## Cover
MAADEN ARGP DIGITALIZATION PLATFORM
MASTER EXECUTION ROADMAP
Year 1 Build + Year 2-5 Maintenance
Client | Maaden - Saudi Arabian Mining Company
Project | Ar Rjum Gold Project (ARGP)
Location | Ar Rjum, Kingdom of Saudi Arabia
SoW Reference | ARGP-DIGI-APP-SOW-001 Rev. 00 (02 April 2025)
XDH Reference | XDH-AE-Q26-05-00030
Programme Duration | Year 1: 40 weeks (10 months) ¦ Year 2-5: continuous maintenance
Team Structure | 7-role lean team (XDH-proposed, per current pricing quote)
Currency | AED (SAR equivalent shown where relevant)
Version | 1.0 Master
Prepared By | XD House LLC FZ
Prepared For | Internal XDH team + Maaden stakeholders
Document Owner | XDH Programme Manager
Last Updated | 02 July 2026
SHEETS IN THIS WORKBOOK
1. Cover | This sheet - project meta, sheet index, how to use
2. Overview | SoW context, 5 modules, 4 phases, strategic goals, key KPIs
3. Programme Timeline | Week-by-week phase Gantt for Year 1 + monthly for Year 2-5
4. Task Register (MASTER) | The core reference: every task with date, owner, software, hardware, deliverable
5. Team Roster | 7 roles, seniority, allocation per phase, day rates, total cost
6. Software Stack | Every software tool needed: purpose, licence type, licensee, cost, per phase
7. Hardware & Infra | KSA in-Kingdom cloud, endpoints, mobile devices, dev workstations
8. Integrations Register | All enterprise system integrations (Aconex, P6, SAP, AVEVA, Azure AD, etc.)
9. KSA Compliance | NCA ECC, PDPL, CST CCRF checklist with owner and due dates
10. Deliverables Register | All deliverables per module and phase, acceptance criteria
11. Quality Gates | Phase gate checklists and payment triggers
12. Risk Register | Top 25 risks with impact, likelihood, mitigation, owner
13. Maintenance Year 2-5 | Ongoing support model, SLA, patches, enhancements
14. Meeting Cadence | Meeting types, frequency, attendees, purpose
HOW TO USE THIS MASTER REFERENCE
1. | This workbook is the definitive execution reference for the Maaden ARGP Digitalization Platform delivery.
2. | The Task Register (Sheet 4) is the day-to-day working sheet. Filter by Owner, Phase, or Week to see your active tasks.
3. | Software Stack, Hardware, Integrations, and Compliance sheets are procurement / access checklists - use these to raise ITSM / procurement tickets.
4. | Quality Gates (Sheet 11) drives payment milestones and Maaden acceptance sign-offs. Do not skip.
5. | Risk Register (Sheet 12) is reviewed weekly at the internal standup and monthly with Maaden PMO.
6. | Update this workbook weekly. Any change to a task date, owner, or deliverable is logged in the "Last Updated" column.
7. | This workbook overrides the initial fee proposal on scope details; the fee proposal governs commercial terms.
CONFIDENTIAL - XDH Internal + Maaden Nominated Recipients Only

## Overview
Maaden ARGP Digitalization Platform - Overview
Reference: ARGP-DIGI-APP-SOW-001 Rev. 00
STRATEGIC GOALS
Unified Data Environment | Centralize all project data, break silos between stakeholders. Single source of truth for ARGP.
Predictive Project Controls | Use AI/ML for proactive insights into schedule, cost, quality, safety risks. AI-powered dashboards.
Digital Workface Transformation | Enable efficiency through digital work packaging (EWP/CWP/IWP), constraint management, real-time progress.
Seamless Digital Handover | Data-rich transition from construction to commissioning. Automated MC Dossier compilation.
Compliance & Security | KSA cybersecurity (NCA ECC), data privacy (PDPL), cloud (CST CCRF). In-Kingdom hosting.
Replicable Blueprint | ARGP is a template for future Maaden mega-projects. Modular, scalable design.
5 CORE MODULES (per SoW 3.1 to 3.5)
M1: Common Data Environment (CDE) & Engineering Data Hub | Federated 3D Model Viewer (Navisworks, Revit, Plant 3D), Document Management with automated workflows, Intelligent P&ID Management (clickable tags), Master Data Registry (MEL, Tag Registers, System/Sub-System breakdowns).
M2: Construction Management & AWP | Digital Work Packaging (EWP/CWP/IWP), Constraint Management Kanban, Progress Measurement + AI-powered field verification, Timesheets and productivity tracking linked to IWPs.
M3: Pre-Commissioning & Mechanical Completion | Digital Pre-Comm Plan template + workflow, MC Package Assembly (auto MC Dossier), Digital Check Sheets and Procedures (mobile), Master Punch List Database with aging reports.
M4: Quality Management & Assurance | Baseline modules (Phase 1) + next modules (Phase 2). NCR management, ITP tracking, welding QA, NDT records, supplier quality.
M5: Procurement & Supply Chain Management | MRQ/RFQ workflows, PO tracking with SAP integration, expediting reports, inspection records, supplier performance.
4 IMPLEMENTATION PHASES (per SoW 3.3.10)
Phase 1 (Weeks 1-4) · Requirement Finalization + Environment Setup + Core Configuration | Kickoff, BEP, requirements workshops, KSA in-Kingdom cloud provisioning (Azure Riyadh / Oracle Riyadh / STC Cloud), enterprise integrations design, NCA ECC baseline, IAM/SSO configuration, sandbox environments live. Peak team: 5.5 FTE.
Phase 2 (Weeks 5-12) · Pilot Module Deployment | Pilot rollout of AWP (M2), Punch List (M3), Pre-Commissioning (M3) on a selected ARGP project area. Enterprise integrations (Aconex, P6, SAP, AVEVA PI). AI agent development (progress verification, RFI turnaround). UAT prep. Peak team: 15 FTE.
Phase 3 (Weeks 13-16) · Pilot Validation + KPI Measurement + Training | KPI measurement against SoW Section 4 metrics. User training (super users, end users, ICT support). Feedback incorporation. Defect remediation. Pilot acceptance memo. Peak team: 6.5 FTE.
Phase 4 (Weeks 17-40) · Full-Scale Rollout | Progressive rollout of M1 (CDE), M4 (Quality), M5 (Procurement) across entire ARGP. Multi-tenant scale, performance tuning, executive dashboards, ongoing training. Final Acceptance at W40. Peak team: 8 FTE.
KEY KPIs (per SoW)
Schedule Certainty | Reduce schedule variance to <5% between planned and actual milestones
Capital Efficiency | Reduce rework by 30% via digital field verification and constraint management
Data Quality | Achieve >95% data quality score via automated cleansing and scoring
User Adoption | >80% daily active users of AWP module within 3 months of full rollout
RFI Turnaround | Median RFI turnaround <5 working days
MC Dossier Completeness | 100% MC Dossiers auto-compiled at handover, zero missing documents
Punch List Ageing | No open A/B punch items >30 days at MC
System Uptime | 99.5% availability of platform during working hours

## Programme Timeline
Programme Timeline - Weekly Gantt (Year 1) + Monthly (Year 2-5)
Y1 assumes PO effective 05 January 2026. Y1 ends: ~15 October 2026 (W40). Y2-5: 12 months each of maintenance.
Phase / Workstream | Owner | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40
PHASE 1: Requirement + Env Setup | All 7 roles | P1 | P1 | P1 | P1
PHASE 2: Pilot Module Deployment | All 7 roles |  |  |  |  | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2
PHASE 3: Pilot Validation + Training | All 7 roles | [12 empty] | P3 | P3 | P3 | P3
PHASE 4: Full-Scale Rollout | All 7 roles | [16 empty] | P4 | P4 | P4 | P4 | P4 | P4 | P4 | P4 | P4 | P4 | P4 | P4 | P4 | P4 | P4 | P4 | P4 | P4 | P4 | P4 | P4 | P4 | P4 | P4
MODULE ACTIVATIONS
M1: CDE + Engineering Data Hub | Module Specialist | [16 empty] | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M
M2: Construction + AWP (PILOT) | Module Specialist |  |  |  |  | M | M | M | M | M | M | M | M
M2: Construction + AWP (FULL) | Module Specialist | [16 empty] | M | M | M | M | M | M | M | M | M | M | M | M | M | M
M3: Pre-Comm + MC (PILOT) | Module Specialist |  |  |  |  | M | M | M | M | M | M | M | M
M3: Pre-Comm + MC (FULL) | Module Specialist | [16 empty] | M | M | M | M | M | M | M | M | M | M | M | M | M | M
M4: Quality Management | Module Specialist | [19 empty] | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M
M5: Procurement + Supply Chain | Module Specialist | [24 empty] | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M
ENTERPRISE INTEGRATIONS
Azure AD / ADFS SSO | Sol Architect |  | I | I | I | I | I
Aconex API integration | Sol Architect |  |  | I | I | I | I | I | I | I | I
Primavera P6 API | Sol Architect |  |  |  | I | I | I | I | I | I | I | I
SAP MM/PS integration | Sol Architect | [5 empty] | I | I | I | I | I | I | I | I | I | I
AVEVA PI real-time data | Sol Architect | [7 empty] | I | I | I | I | I | I | I | I | I | I | I
MS EPM integration | Sol Architect | [9 empty] | I | I | I | I | I | I | I
SIEM logging | KSA Security |  |  | I | I | I | I | I | I
KSA COMPLIANCE MILESTONES
NCA ECC-1:2018 baseline | KSA Security | C | C | C
PDPL data privacy design | KSA Security |  | C | C | C
CST CCRF cloud residency proof | KSA Security | C | C
Pen test (external) | KSA Security | [13 empty] | C | C
ISO 27001 pre-audit | KSA Security | [29 empty] | C | C | C
QUALITY GATES / PAYMENT TRIGGERS
G1: Requirements Sign-off | PM |  |  |  | G
G2: Pilot UAT Complete | PM | [11 empty] | G
G3: Pilot Acceptance | PM | [15 empty] | G
G4: M2/M3 Full Live | PM | [23 empty] | G
G5: M1/M4 Full Live | PM | [31 empty] | G
G6: M5 Live + Final Acceptance | PM | [39 empty] | G
YEAR 2 - 5 · MAINTENANCE + ENHANCEMENT (monthly view)
Activity | Owner | Y2 | Y3 | Y4 | Y5
L1/L2/L3 Support | PM + Module | X | X | X | X
Bug fixes + patches (2x / yr) | DBA + Module | X | X | X | X
Feature enhancements (5% budget) | Sol Architect | X | X | X | X
KPI dashboards refresh | AI/ML | X | X | X | X
Annual NCA ECC audit | KSA Security | X | X | X | X
PDPL annual attestation | KSA Security | X | X | X | X
Unreal Engine / stack upgrade | DBA |  | X |  | X
Multi-tenant expansion (other Maaden projects) | Sol Architect |  | X | X | X
End of contract handover | PM |  |  |  | X
LEGEND
Phase 1
P2 | Phase 2
P3 | Phase 3
P4 | Phase 4
M | Module rollout
I | Integration
C | Compliance
G | Quality Gate
X | Maintenance activity

## Task Register (MASTER)
TASK REGISTER - MASTER EXECUTION REFERENCE
Filter by Phase, Week, or Owner to see your active tasks. Update Status column weekly.
Task ID | Phase | Week | Start | End | Task | Owner (role) | Software Required | Hardware / Infra | Dependencies | Deliverable | Quality Gate / Acceptance | SoW Ref | Status | Notes
T-001 | P1 | W1 | 05 Jan 2026 | 09 Jan 2026 | Contract effective + PO acknowledgement | Programme Manager | MS Teams, MS Word | None | (Contract signed) | PO log, contract file archived, kickoff email to XDH team | PM signs internal handover | SoW 3.4.8 | Not started | Day 1
T-002 | P1 | W1 | 05 Jan 2026 | 09 Jan 2026 | Internal kickoff (XDH team) | Programme Manager | MS Teams | None | T-001 | Kickoff deck, roles + responsibilities matrix, RACI | PM sign-off | Internal | Not started | Day 1-2
T-003 | P1 | W1 | 05 Jan 2026 | 09 Jan 2026 | Client kickoff with Maaden PMO | Programme Manager, Solution Architect | MS Teams, MS PowerPoint | Maaden meeting room (video) | T-002 | Meeting minutes, action log, agreed communication cadence | Maaden PMO sign-off | SoW 3.4.8 | Not started | Day 2-3
T-004 | P1 | W1 | 05 Jan 2026 | 09 Jan 2026 | BEP (BIM Execution Plan) v0.5 draft | Programme Manager, Solution Architect, Doc Controller | MS Word, MS Visio | None | T-003 | BEP v0.5 covering scope, deliverables, roles, standards | Draft circulated to team | SoW 3.4.5 | Not started | Day 3-5
T-005 | P1 | W1 | 05 Jan 2026 | 09 Jan 2026 | KSA in-Kingdom cloud tenancy request | KSA Security Lead, DBA | Azure Portal (Riyadh), Oracle Cloud Console | Azure Riyadh region | T-001 | Tenancy provisioned in KSA region with correct residency zone | Maaden ICT sign-off | SoW 4.2, CST CCRF | Not started | Critical path
T-006 | P1 | W1 | 05 Jan 2026 | 09 Jan 2026 | Azure AD / ADFS SSO connection request | KSA Security Lead, Solution Architect | Azure AD, ADFS console | Maaden ADFS server | T-005 | SSO tenant registered, service principal created | Maaden ICT sign-off | SoW 3.4.4 | Not started
T-007 | P1 | W1 | 05 Jan 2026 | 09 Jan 2026 | Maaden enterprise system access request forms | Solution Architect, Doc Controller | ServiceNow / Maaden ITSM | None | T-003 | Access requests raised for Aconex, P6, SAP, AVEVA PI, MS EPM | Maaden ITSM approval | SoW 4.1 | Not started | Track weekly
T-010 | P1 | W2 | 12 Jan 2026 | 16 Jan 2026 | Requirements workshop Series #1 (M1: CDE + Engineering Data) | Module Specialist, Solution Architect | Miro / Mural, MS Teams | Maaden meeting room | T-003 | Workshop minutes, functional requirements v0.1 for M1 | Maaden PMO sign-off | SoW 3.1 | Not started | Full week workshop
T-011 | P1 | W2 | 12 Jan 2026 | 16 Jan 2026 | Requirements workshop Series #2 (M2: Construction + AWP) | Module Specialist, Solution Architect | Miro / Mural, MS Teams | Maaden meeting room | T-003 | Workshop minutes, functional requirements v0.1 for M2 | Maaden PMO sign-off | SoW 3.2 | Not started
T-012 | P1 | W2 | 12 Jan 2026 | 16 Jan 2026 | Data mapping and source system inventory | Solution Architect, DBA | MS Excel, Visio, Draw.io | Read access to sandbox environments | T-007 | Data source register, master data mapping v0.1 | PM review | SoW 3.4.4 | Not started
T-013 | P1 | W2 | 12 Jan 2026 | 16 Jan 2026 | NCA ECC-1:2018 baseline assessment start | KSA Security Lead | NCA ECC assessment tool, MS Excel | None | T-005 | ECC gap analysis v0.1 | Report to Maaden CISO | NCA ECC-1:2018 | Not started | KSA regulator req.
T-014 | P1 | W2 | 12 Jan 2026 | 16 Jan 2026 | Sandbox environment provisioning start | DBA, Solution Architect | Azure Portal, Terraform, GitHub | Azure Riyadh region | T-005 | Dev + UAT + Perf sandbox templates ready | Sandbox login test passes | SoW 4.1 | Not started
T-020 | P1 | W3 | 19 Jan 2026 | 23 Jan 2026 | Requirements workshop Series #3 (M3: Pre-Comm + MC) | Module Specialist, Solution Architect | Miro / Mural, MS Teams | Maaden meeting room | T-003 | Workshop minutes, functional requirements v0.1 for M3 | Maaden PMO sign-off | SoW 3.3 | Not started
T-021 | P1 | W3 | 19 Jan 2026 | 23 Jan 2026 | Requirements workshop Series #4 (M4: Quality) | Module Specialist, Solution Architect | Miro / Mural, MS Teams | Maaden meeting room | T-003 | Workshop minutes, functional requirements v0.1 for M4 | Maaden PMO sign-off | SoW 3.4 | Not started
T-022 | P1 | W3 | 19 Jan 2026 | 23 Jan 2026 | Solution Architecture v0.5 draft | Solution Architect | MS Visio, Enterprise Architect, MS Word | None | T-010, T-011, T-012 | Solution Architecture document v0.5 covering all 5 modules | Internal design review | SoW 4.1 | Not started
T-023 | P1 | W3 | 19 Jan 2026 | 23 Jan 2026 | Enterprise integrations design (Aconex, P6, SAP, AVEVA PI) | Solution Architect | Postman, Swagger, MS Visio | Aconex sandbox, P6 sandbox | T-007 | Integration Architecture v0.5, API contract drafts | Internal review | SoW 4.1 | Not started | Blocker if delayed
T-024 | P1 | W3 | 19 Jan 2026 | 23 Jan 2026 | Data Privacy Impact Assessment (PDPL) | KSA Security Lead, Doc Controller | MS Word | None | T-013 | DPIA report v0.5 per PDPL | Maaden DPO review | PDPL | Not started
T-025 | P1 | W3 | 19 Jan 2026 | 23 Jan 2026 | CST CCRF cloud residency compliance memo | KSA Security Lead | MS Word | None | T-005 | Written attestation of in-Kingdom hosting compliance | Maaden ICT sign-off | CST CCRF | Not started
T-026 | P1 | W3 | 19 Jan 2026 | 23 Jan 2026 | Enterprise Access Provisioning (Aconex, P6, SAP, AVEVA PI, MS EPM) | Solution Architect, DBA | Aconex, P6, SAP GUI, AVEVA PI | None | T-007 | Login credentials tested for all 7 XDH team members | Test connection log | SoW 4.1 | Not started
T-030 | P1 | W4 | 26 Jan 2026 | 30 Jan 2026 | Requirements workshop Series #5 (M5: Procurement + Supply Chain) | Module Specialist, Solution Architect | Miro / Mural, MS Teams | Maaden meeting room | T-003 | Workshop minutes, functional requirements v0.1 for M5 | Maaden PMO sign-off | SoW 3.5 | Not started
T-031 | P1 | W4 | 26 Jan 2026 | 30 Jan 2026 | Consolidated Requirements Document v1.0 | Solution Architect, Module Specialist | MS Word, Confluence | None | T-010, T-011, T-020, T-021, T-030 | Requirements v1.0 across 5 modules signed off by Maaden | Maaden PMO sign-off | SoW 3.4.5 | Not started | Phase 1 exit criteria
T-032 | P1 | W4 | 26 Jan 2026 | 30 Jan 2026 | BEP v1.0 - final | Programme Manager, Solution Architect, Doc Controller | MS Word | None | T-004, T-031 | BEP v1.0 signed off | Maaden PMO sign-off | SoW 3.4.5 | Not started | Phase 1 exit criteria
T-033 | P1 | W4 | 26 Jan 2026 | 30 Jan 2026 | Environment build-out (Dev, UAT, Perf, Prod skeleton) | DBA, Solution Architect | Azure Portal, Terraform, GitHub Actions | Azure Riyadh region | T-014 | All environments ready with baseline security | Environment sanity test | SoW 4.1, 4.2 | Not started
T-034 | P1 | W4 | 26 Jan 2026 | 30 Jan 2026 | Phase 1 Quality Gate review | Programme Manager, ALL team + Maaden PMO | MS Teams, MS PowerPoint | Maaden meeting room | T-031, T-032, T-033 | G1 sign-off memo, Phase 2 mobilisation approval | MAADEN PMO SIGN-OFF (PAYMENT TRIGGER) | SoW 3.3.10 | Not started | GATE 1 - 15% payment released
T-050 | P2 | W5 | 02 Feb 2026 | 06 Feb 2026 | Sprint 1 kickoff (M2 AWP pilot build) | Solution Architect, Module Specialist, AI/ML Engineer | Jira, GitHub, VS Code, Azure DevOps | Dev environment | T-034 | Sprint 1 backlog with 20-30 stories, tech design docs | Internal sprint planning | SoW 3.2 | Not started
T-051 | P2 | W5 | 02 Feb 2026 | 06 Feb 2026 | AI/ML pipeline design (progress verification, RFI turnaround) | AI/ML Engineer, Solution Architect | Python, Jupyter, Databricks, MLflow | Databricks Riyadh region | T-023 | AI/ML architecture doc, model selection (Anthropic Claude API) | Internal review | SoW 3.3.4 | Not started
T-052 | P2 | W5 | 02 Feb 2026 | 06 Feb 2026 | Aconex integration development starts | Solution Architect, DBA | Postman, VS Code, Azure API Mgmt | Aconex sandbox | T-023 | API adapter for Aconex v0.5 (docs sync) | Internal review | SoW 4.1 | Not started
T-053 | P2 | W5 | 02 Feb 2026 | 06 Feb 2026 | KSA onsite mobilisation (Ar Rjum site) | Programme Manager (partial), Module Specialist | None | Site laptop, mobile phone, hard hat | T-034 | Site badges issued, HSE induction complete | Site supervisor sign-off | SoW 3.4.6 | Not started | PPE required
T-060 | P2 | W6 | 09 Feb 2026 | 13 Feb 2026 | AWP IWP Data Model build (M2) | AI/ML Engineer, DBA | Postgres, Azure SQL, dbt | Dev environment | T-050 | IWP schema, Kanban states, permission matrix | Code review | SoW 3.2 | Not started
T-061 | P2 | W6 | 09 Feb 2026 | 13 Feb 2026 | Primavera P6 API integration | Solution Architect | Postman, VS Code, Node.js | P6 sandbox | T-052 | P6 API adapter v0.5 (baseline sync) | Integration test passes | SoW 4.1 | Not started
T-062 | P2 | W6 | 09 Feb 2026 | 13 Feb 2026 | AI agent #1 - Progress Verification | AI/ML Engineer | Python, Anthropic Claude API, Azure OpenAI | GPU node in Azure | T-051 | AI agent prototype ingesting IWP data + producing progress % | Internal demo | SoW 3.3.4 | Not started
T-063 | P2 | W6 | 09 Feb 2026 | 13 Feb 2026 | Punch List Master Database schema (M3) | DBA, Module Specialist | Postgres, Azure SQL | Dev environment | T-034 | Punch List schema with ageing report views | Code review | SoW 3.3 | Not started
T-064 | P2 | W6 | 09 Feb 2026 | 13 Feb 2026 | SIEM logging integration | KSA Security Lead | Splunk / Azure Sentinel | SIEM tenant | T-005 | Application logs streaming to SIEM | Log query test passes | NCA ECC | Not started
T-070 | P2 | W7 | 16 Feb 2026 | 20 Feb 2026 | Sprint 2 (AWP UI + workflow) | Solution Architect, Module Specialist | React, Next.js, Tailwind, Azure DevOps | Dev environment | T-060 | AWP UI v0.5 with IWP CRUD + Kanban | Sprint review | SoW 3.2 | Not started
T-071 | P2 | W7 | 16 Feb 2026 | 20 Feb 2026 | SAP MM/PS API integration | Solution Architect, DBA | SAP GUI, SAP OData, VS Code | SAP sandbox | T-061 | SAP adapter v0.5 (Materials + PS) | Integration test passes | SoW 4.1 | Not started
T-072 | P2 | W7 | 16 Feb 2026 | 20 Feb 2026 | AI agent #2 - RFI Turnaround Predictor | AI/ML Engineer | Python, Anthropic Claude, HuggingFace | GPU node in Azure | T-062 | AI agent for RFI prioritisation and predicted turnaround | Internal demo | SoW 3.3.4 | Not started
T-073 | P2 | W7 | 16 Feb 2026 | 20 Feb 2026 | Mobile app scaffold (iOS + Android) | Solution Architect | React Native, Xcode, Android Studio | Test devices (iPad, Android tablet) | T-070 | Mobile app skeleton with SSO + offline sync | Test on 2 devices | SoW 3.3 | Not started
T-080 | P2 | W8 | 23 Feb 2026 | 27 Feb 2026 | Mid-phase demo to Maaden PMO | Programme Manager, Solution Architect, Module Specialist | MS Teams, MS PowerPoint | None | T-070, T-071, T-072 | Demo video, feedback log, Q&A minutes | Maaden PMO feedback in writing | SoW 3.4 | Not started | MID-PHASE CHECK
T-081 | P2 | W8 | 23 Feb 2026 | 27 Feb 2026 | AVEVA PI real-time data pipe | Solution Architect, DBA | AVEVA PI System Explorer, Python | AVEVA PI Server access | T-071 | PI tag mapping doc, real-time data flowing to platform | End-to-end test passes | SoW 4.1 | Not started
T-082 | P2 | W8 | 23 Feb 2026 | 27 Feb 2026 | AI agent #3 - Schedule Predictability | AI/ML Engineer | Python, Prophet, XGBoost, Databricks | GPU node | T-081 | Schedule risk forecast model + dashboard | Internal demo | SoW 3.3.4 | Not started
T-083 | P2 | W8 | 23 Feb 2026 | 27 Feb 2026 | Pre-Commissioning digital checksheet builder (M3) | Module Specialist, Solution Architect | React, form.io, Azure DevOps | Dev environment | T-063 | Checksheet templates for flushing, cleaning, calibration, loop test | Module Specialist sign-off | SoW 3.3 | Not started
T-090 | P2 | W9 | 02 Mar 2026 | 06 Mar 2026 | MC Dossier auto-assembly logic | Module Specialist, AI/ML Engineer | Python, Postgres, Azure Blob Storage | Dev environment | T-083 | Auto-compilation of MC Dossier from linked documents | Test on 5 sample systems | SoW 3.3 | Not started
T-091 | P2 | W9 | 02 Mar 2026 | 06 Mar 2026 | AI agent #4 - Punch List Ageing + Escalation | AI/ML Engineer | Python, Anthropic Claude | GPU node | T-063 | AI agent that scores punch items and escalates aged tickets | Internal demo | SoW 3.3.4 | Not started
T-092 | P2 | W9 | 02 Mar 2026 | 06 Mar 2026 | MS EPM integration | Solution Architect, DBA | MS Project Server, MS EPM API | MS EPM sandbox | T-071 | EPM sync adapter v0.5 | Integration test passes | SoW 4.1 | Not started
T-100 | P2 | W10 | 09 Mar 2026 | 13 Mar 2026 | End-to-end integration testing | Solution Architect, DBA, Module Specialist | Postman, JMeter, Selenium | UAT environment | T-052, T-061, T-071, T-081, T-092 | Integration test report, 0 P1 defects | Test pass 95%+ | SoW 3.4.4 | Not started
T-101 | P2 | W10 | 09 Mar 2026 | 13 Mar 2026 | Performance testing (M2 + M3 pilot) | DBA, Solution Architect | JMeter, Azure Load Test | Perf environment | T-100 | Load test report, response times documented | Meets SLA | SoW 3.4.4 | Not started
T-102 | P2 | W10 | 09 Mar 2026 | 13 Mar 2026 | Pen test (external firm engaged) | KSA Security Lead | Burp Suite (external), OWASP ZAP | UAT environment | T-100 | Pen test report v1.0 | External auditor sign-off | NCA ECC | Not started | Book 6 weeks ahead
T-103 | P2 | W11 | 16 Mar 2026 | 20 Mar 2026 | UAT scripts + test data preparation | Module Specialist, Doc Controller | MS Excel, Confluence, TestRail | UAT environment | T-100 | ~200 UAT test scripts across M2 and M3 | Internal QA sign-off | SoW 3.4.5 | Not started
T-104 | P2 | W11 | 16 Mar 2026 | 20 Mar 2026 | Super-user training (M2 + M3 pilot users) | Module Specialist, Programme Manager | MS Teams, Docebo LMS, MS PowerPoint | UAT environment | T-103 | Training deck, super-user certification | Attendance sheet, quiz pass | SoW 3.4.5 | Not started
T-110 | P2 | W12 | 23 Mar 2026 | 27 Mar 2026 | Pilot deployment on selected ARGP area | Solution Architect, DBA, Module Specialist | Azure DevOps, GitHub Actions | Production environment | T-100, T-102, T-103, T-104 | Pilot LIVE for ARGP selected area, 50-100 users onboarded | PM sign-off | SoW 3.3.10 | Not started | GO-LIVE
T-111 | P2 | W12 | 23 Mar 2026 | 27 Mar 2026 | Phase 2 Quality Gate review | Programme Manager, ALL team + Maaden PMO | MS Teams, MS PowerPoint | Maaden meeting room | T-110 | G2 sign-off memo | MAADEN PMO SIGN-OFF (PAYMENT TRIGGER) | SoW 3.3.10 | Not started | GATE 2 - 20% payment released
T-130 | P3 | W13 | 30 Mar 2026 | 03 Apr 2026 | KPI measurement setup (per SoW Section 4) | AI/ML Engineer, Solution Architect | Power BI, Databricks, MS Excel | Prod environment | T-110 | KPI dashboards live for all 8 SoW KPIs | Baseline metrics captured | SoW 3.4.4 | Not started
T-131 | P3 | W13 | 30 Mar 2026 | 03 Apr 2026 | Extended user training (end-users, ICT Support) | Module Specialist, Programme Manager | Docebo LMS, MS Teams | Maaden training room + remote | T-104 | All ARGP end users + ICT Support trained (100+ people) | Attendance + quiz results | SoW 3.4.5 | Not started
T-132 | P3 | W14 | 06 Apr 2026 | 10 Apr 2026 | Pilot week-1 monitoring + defect triage | ALL team | Jira, PagerDuty, Datadog | Prod environment | T-110 | Daily standup notes, defect log | Zero unresolved P1 | SoW 3.3.10 | Not started
T-133 | P3 | W14 | 06 Apr 2026 | 10 Apr 2026 | Feedback consolidation from pilot users | Programme Manager, Module Specialist | MS Forms, Confluence | None | T-132 | Feedback report v1.0 with top 20 improvement asks | Report to Maaden PMO | SoW 3.3.10 | Not started
T-134 | P3 | W15 | 13 Apr 2026 | 17 Apr 2026 | Sprint - defect remediation + top feedback items | ALL dev team | Jira, VS Code, Azure DevOps | Dev + UAT environments | T-133 | v1.1 patch with top 20 items deployed | Regression test passes | SoW 3.3.10 | Not started
T-135 | P3 | W15 | 13 Apr 2026 | 17 Apr 2026 | Pen test remediation (from T-102) | KSA Security Lead, DBA | Various security tools | UAT environment | T-102 | All Critical + High findings closed | External re-test passes | NCA ECC | Not started
T-136 | P3 | W16 | 20 Apr 2026 | 24 Apr 2026 | Pilot Acceptance Test | Programme Manager, Maaden PMO | MS Teams, TestRail | Prod environment | T-130, T-131, T-132, T-133, T-134 | Pilot Acceptance Memo signed by Maaden | MAADEN PMO SIGN-OFF (PAYMENT TRIGGER) | SoW 3.3.10 | Not started | GATE 3 - 15% payment released
T-137 | P3 | W16 | 20 Apr 2026 | 24 Apr 2026 | Phase 3 gate review + Phase 4 mobilisation planning | Programme Manager, Solution Architect | MS Teams, MS Project | None | T-136 | Phase 4 detailed plan, resource plan for W17-W40 | Internal + Maaden PMO approval | Internal | Not started
T-170 | P4 | W17 | 27 Apr 2026 | 01 May 2026 | M2/M3 full-scale rollout kickoff (all ARGP areas) | Programme Manager, Module Specialist | MS Project, Docebo LMS | Prod environment | T-136 | M2/M3 available to all ~500 ARGP users | PM sign-off | SoW 3.3.10 | Not started
T-171 | P4 | W17 | 27 Apr 2026 | 01 May 2026 | M1 CDE build kickoff (Federated Model Viewer) | Solution Architect, Module Specialist, AI/ML Engineer | Autodesk Forge / APS, Navisworks, IFC.js | Dev environment | T-136 | M1 sprint backlog, tech design for Federated Viewer | Internal review | SoW 3.1 | Not started
T-172 | P4 | W18 | 04 May 2026 | 08 May 2026 | Intelligent P&ID Management (clickable tag) - M1 | AI/ML Engineer, Module Specialist | Python, OCR (Tesseract), AutoCAD API | Dev environment | T-171 | P&ID digitisation prototype for 50 sample sheets | Test on real P&IDs | SoW 3.1 | Not started
T-173 | P4 | W19 | 11 May 2026 | 15 May 2026 | Master Data Registry (MEL, Tag Register, System/Subsystem) | DBA, Module Specialist | Postgres, Azure Data Factory | Dev environment | T-172 | Master Data Registry v0.5 with 5000+ tags loaded | Data quality > 95% | SoW 3.1 | Not started
T-174 | P4 | W20 | 18 May 2026 | 22 May 2026 | Document Management workflow build | Solution Architect, Module Specialist | Node.js, Aconex API, Azure Storage | Dev environment | T-171 | Automated transmittal + approval workflow live | Round-trip test passes | SoW 3.1 | Not started
T-210 | P4 | W21 | 25 May 2026 | 29 May 2026 | M4 Quality build kickoff | Module Specialist, Solution Architect | Jira, VS Code, Azure DevOps | Dev environment | T-136 | M4 sprint backlog covering NCR, ITP, NDT, welding QA | Internal review | SoW 3.4 | Not started
T-211 | P4 | W22 | 01 Jun 2026 | 05 Jun 2026 | NCR (Non-Conformance Report) workflow | Module Specialist, AI/ML Engineer | React, Node.js, AI classification | Dev environment | T-210 | NCR workflow with AI-classification of NCRs | End-to-end test | SoW 3.4 | Not started
T-212 | P4 | W23 | 08 Jun 2026 | 12 Jun 2026 | ITP (Inspection Test Plan) tracking | Module Specialist | React, Azure DevOps | Dev environment | T-211 | ITP tracker with linked witness / hold points | Module Specialist sign-off | SoW 3.4 | Not started
T-213 | P4 | W24 | 15 Jun 2026 | 19 Jun 2026 | Welding QA + NDT records | Module Specialist, DBA | React, Azure DevOps | Dev environment, 3rd-party NDT lab feed | T-212 | Welding + NDT records module live | Test with lab data | SoW 3.4 | Not started
T-214 | P4 | W24 | 15 Jun 2026 | 19 Jun 2026 | M1 CDE full launch (all viewers, doc mgmt, P&ID, master data) | Solution Architect, Module Specialist, DBA | Azure DevOps, GitHub Actions | Prod environment | T-171, T-172, T-173, T-174 | M1 CDE LIVE for all users | PM sign-off | SoW 3.1 | Not started
T-215 | P4 | W24 | 15 Jun 2026 | 19 Jun 2026 | Gate G4: M2/M3 full live + M1 live | Programme Manager, Maaden PMO | MS Teams | Maaden meeting room | T-170, T-214 | G4 sign-off memo | MAADEN PMO SIGN-OFF (PAYMENT TRIGGER) | SoW 3.3.10 | Not started | GATE 4 - 15% payment released
T-250 | P4 | W25 | 22 Jun 2026 | 26 Jun 2026 | M5 Procurement + Supply Chain build kickoff | Module Specialist, Solution Architect | Jira, VS Code | Dev environment | T-215 | M5 sprint backlog (MRQ, RFQ, PO, expediting, inspection) | Internal review | SoW 3.5 | Not started
T-251 | P4 | W26 | 29 Jun 2026 | 03 Jul 2026 | MRQ / RFQ workflow with SAP integration | Module Specialist, Solution Architect | React, SAP OData | Dev, SAP sandbox | T-250 | MRQ/RFQ workflow live with SAP round-trip | End-to-end test passes | SoW 3.5 | Not started
T-252 | P4 | W27 | 06 Jul 2026 | 10 Jul 2026 | PO tracking + expediting dashboard | Module Specialist, DBA | React, PowerBI, SAP | Dev environment | T-251 | PO dashboard with slippage alerts | Module Specialist sign-off | SoW 3.5 | Not started
T-253 | P4 | W28 | 13 Jul 2026 | 17 Jul 2026 | Supplier inspection records module | Module Specialist | React, Azure Blob Storage | Dev, mobile devices for inspectors | T-252 | Inspection records module live on desktop + mobile | Field test passes | SoW 3.5 | Not started
T-254 | P4 | W29 | 20 Jul 2026 | 24 Jul 2026 | M4 Quality full launch | Module Specialist, Solution Architect | Azure DevOps | Prod environment | T-213 | M4 Quality LIVE for all users | PM sign-off | SoW 3.4 | Not started
T-255 | P4 | W30 | 27 Jul 2026 | 31 Jul 2026 | Supplier performance analytics | AI/ML Engineer, Module Specialist | Power BI, Python | Prod environment | T-253 | Supplier scorecard live | Baseline metrics | SoW 3.5 | Not started
T-256 | P4 | W32 | 10 Aug 2026 | 14 Aug 2026 | M5 Procurement full launch | Module Specialist, Solution Architect | Azure DevOps | Prod environment | T-251, T-252, T-253, T-255 | M5 LIVE for all Procurement users | PM sign-off | SoW 3.5 | Not started
T-330 | P4 | W33 | 17 Aug 2026 | 21 Aug 2026 | Gate G5: M1/M4 full live | Programme Manager | MS Teams | Maaden meeting room | T-214, T-254 | G5 sign-off memo | MAADEN PMO SIGN-OFF (PAYMENT TRIGGER) | SoW 3.3.10 | Not started | GATE 5 - 10% payment released
T-331 | P4 | W33 | 17 Aug 2026 | 21 Aug 2026 | Performance tuning + scalability | DBA, Solution Architect | Azure Monitor, Application Insights, JMeter | Prod environment | T-256 | Performance tuning report, all SLAs met at 500+ concurrent users | Load test passes | SoW 4.1 | Not started
T-332 | P4 | W34 | 24 Aug 2026 | 28 Aug 2026 | Executive dashboards (Maaden C-suite) | AI/ML Engineer, Programme Manager | Power BI Premium | Prod environment | T-130, T-331 | Exec dashboard live for Maaden CFO, CIO, CPO | Exec sign-off | SoW 3.4.4 | Not started
T-333 | P4 | W35 | 31 Aug 2026 | 04 Sep 2026 | ISO 27001 pre-audit | KSA Security Lead | External auditor | Prod environment | T-135, T-331 | Pre-audit report, all findings actionable | Auditor sign-off | NCA ECC, ISO 27001 | Not started
T-334 | P4 | W36 | 07 Sep 2026 | 11 Sep 2026 | End-user training rollout (all ~500 users) | Module Specialist, Programme Manager | Docebo LMS | Maaden training centre + remote | T-256 | All users trained + certified | Attendance + quiz results | SoW 3.4.5 | Not started
T-335 | P4 | W38 | 21 Sep 2026 | 25 Sep 2026 | Documentation + handover pack | Doc Controller, Programme Manager | MS Word, Confluence | None | ALL | User Manual v1.0, Admin Manual v1.0, Technical Doc, Runbook, Playbooks | Doc Controller sign-off | SoW 3.4.5 | Not started
T-336 | P4 | W39 | 28 Sep 2026 | 02 Oct 2026 | Knowledge transfer to Maaden ICT Support | Solution Architect, DBA, KSA Security | MS Teams, Confluence, Runbooks | None | T-335 | ICT Support handover complete, L1/L2/L3 escalation matrix | ICT Support sign-off | SoW 3.4.7 | Not started
T-337 | P4 | W40 | 05 Oct 2026 | 09 Oct 2026 | Gate G6: Final Acceptance + Year 1 Closure | Programme Manager, ALL team + Maaden CFO/CIO | MS Teams, MS PowerPoint | Maaden HQ | T-333, T-334, T-335, T-336 | Final Acceptance Certificate signed | MAADEN CFO/CIO SIGN-OFF (FINAL PAYMENT) | SoW 3.3.10 | Not started | GATE 6 - 10% final payment + Y1 close
T-Y2-1 | Y2-5 | Ongoing | Year 2+ | Year 5 | Year 2 - Continuous L1/L2/L3 support (24/7 KSA) | Programme Manager, Module Specialist, DBA | PagerDuty, Datadog, ServiceNow | Prod environment | T-337 | Monthly SLA report, 99.5% uptime target | SLA report to Maaden | SoW 4.3 | Not started | AED 480K / year
T-Y2-2 | Y2-5 | Ongoing | Year 2+ | Year 5 | Year 2 - Quarterly patches + security updates | DBA, KSA Security Lead | Azure DevOps, Windows Update for Business | Prod environment | T-337 | 4 patch releases per year, security posture maintained | Change ticket log | NCA ECC | Not started
T-Y2-3 | Y2-5 | Ongoing | Year 2+ | Year 5 | Year 2 - Feature enhancement backlog (5% budget) | Solution Architect, Module Specialist | Jira, GitHub | Dev environment | T-337 | Top 10 enhancements delivered | Maaden PMO acceptance | SoW 4.3 | Not started
T-Y2-4 | Y2-5 | Ongoing | Year 2+ | Year 5 | Year 2 - Annual NCA ECC audit | KSA Security Lead | External auditor | Prod environment | T-333 | ECC audit certificate + remediation plan | Regulator sign-off | NCA ECC | Not started | Annual mandatory
T-Y2-5 | Y2-5 | Ongoing | Year 2+ | Year 5 | Year 2 - PDPL annual attestation | KSA Security Lead, Doc Controller | External auditor | None | T-024 | PDPL attestation submitted | Regulator sign-off | PDPL | Not started
T-Y3-1 | Y2-5 | Ongoing | Year 2+ | Year 5 | Year 3 - Unreal Engine / stack upgrade | DBA, Solution Architect | Azure DevOps | Dev + UAT + Prod | T-Y2-1 | Version upgrade completed with zero data loss | Post-upgrade validation | SoW 4.3 | Not started
T-Y3-2 | Y2-5 | Ongoing | Year 2+ | Year 5 | Year 3 - Multi-tenant expansion (other Maaden projects) | Solution Architect, Module Specialist | Azure | Prod environment | T-Y2-1 | Second Maaden project onboarded to platform | Other project PM sign-off | SoW 4.3 | Not started
T-Y5-1 | Y2-5 | Ongoing | Year 2+ | Year 5 | Year 5 - Contract closure + IP handover | Programme Manager, KSA Security | MS Word | None | ALL | Final IP Assignment Certificate signed | Maaden legal sign-off | SoW 4.3 | Not started | End of 5-year contract

## Team Roster
Team Roster & Allocation - 7-Role Lean Team
Base rate: AED 3,300/day (senior consultant) x 22 working days = AED 72,600/mo. PM at AED 4,500/day = AED 99,000/mo.
# | Role | Seniority | Rate (AED/mo) | Phase 1 (1 mo) | Phase 2 (2 mo) | Phase 3 (1 mo) | Phase 4 (6 mo) | Y1 Total (mo) | Y1 Cost (AED) | Responsibility
1 | Programme Manager | Very Senior | 99000 | 1 | 2 | 1 | 8 | 12 | 1188000 | Overall delivery, client interface, escalation, phase gate reviews, weekly PMO report
2 | Solution Architect / Integration Engineer | Very Senior | 72600 | 1 | 4 | 1 | 7 | 13 | 943800 | Architecture, tech stack, enterprise integrations (Aconex, P6, SAP, AVEVA), code reviews, design decisions
3 | Database Administrator (DBA) | Senior | 72600 | 0.5 | 2 | 1 | 8 | 11.5 | 834900 | Data model, KSA cloud infrastructure, backups, patching, performance tuning, MS SQL / Oracle DB (Maaden-approved)
4 | AI / ML Engineer | Senior | 72600 | 0 | 2 | 1 | 8 | 11 | 798600 | 4 AI agents (per SoW 3.3.4): Progress Verification, RFI Turnaround, Schedule Risk, Punch List Escalation
5 | KSA Compliance / Security Lead | Senior | 72600 | 1 | 1 | 0.5 | 3 | 5.5 | 399300 | NCA ECC-1:2018 baseline, PDPL DPIA, CST CCRF residency, SIEM setup, pen test coordination, annual audits
6 | Module Specialist (5 modules coverage) | Senior | 72600 | 1 | 2 | 1 | 8 | 12 | 871200 | Functional depth in M1 (CDE), M2 (AWP), M3 (Pre-Comm), M4 (Quality), M5 (Procurement). Business analysis + UAT lead
7 | Documents Controller | Senior | 72600 | 1 | 2 | 1 | 8 | 12 | 871200 | BEP, MC Dossier compilation, training materials, user manual, admin manual, ISO 19650-compliant records
| TOTAL | [6 empty] | 77 | 5907000
RATE CARD REFERENCE
| Level | Day Rate (AED) | Monthly (AED, 22 days) | Annual (AED, 264 days)
| Partner | 5000 | 110000 | 1320000
| Director / Senior Manager | 4500 | 99000 | 1188000
| Programme Manager | 4500 | 99000 | 1188000
| Senior Consultant / Senior Manager | 3300 | 72600 | 871200
| Consultant | 3300 | 72600 | 871200

## Software Stack
Software Stack - Every Tool Needed
Licences per role/phase. XDH-provided or Maaden-procured flagged. Costs indicative.
# | Software | Category | Phase(s) | Purpose | Licensor | Cost (indicative) | Notes
1 | Microsoft 365 (Teams, Word, Excel, PowerPoint, Visio, Forms) | Productivity | All | Collaboration, docs, dashboards, spec writing | Microsoft (XDH provides) | AED 25/user/mo | Standard XDH stack
2 | Confluence (Cloud) | Documentation | All | Team knowledge base, runbooks, ADRs | Atlassian (XDH provides) | USD 6/user/mo | Central technical wiki
3 | Jira Software | Project Mgmt | P2 onwards | Sprint backlog, defect tracking, roadmap | Atlassian (XDH provides) | USD 8/user/mo | Standard sprint tool
4 | GitHub Enterprise (or Azure DevOps Repos) | Source Control | All | Code repository, CI/CD, code review | Microsoft (XDH provides) | USD 21/user/mo | Includes Copilot
5 | Azure DevOps Pipelines | CI/CD | All | Build + deploy pipelines to Azure Riyadh | Microsoft (Maaden Azure sub) | Included in Azure | KSA-hosted
6 | Visual Studio Code + JetBrains suite | IDE | All | Code editing, debugging, refactoring | Microsoft + JetBrains (XDH) | USD 20/user/mo
7 | Microsoft Azure (Riyadh region) | Cloud Platform | All | In-Kingdom hosting, PaaS services, App Service, SQL DB, Functions | Microsoft (Maaden pays) | USD 15-25K / month | Maaden direct procurement per SoW 4.2
8 | Oracle Cloud (Riyadh) - IF Oracle DB chosen | Cloud Platform | All | Alternative to Azure for DB-heavy workloads | Oracle (Maaden pays) | USD 10-20K / month | Only if Oracle DB path chosen
9 | STC Cloud - IF preferred | Cloud Platform | All | Sovereign KSA cloud option | STC (Maaden pays) | Similar to Azure | Optional per SoW 4.2
10 | Microsoft SQL Server Enterprise (or Azure SQL) | Database | All | Primary transactional DB per Maaden-approved DB technologies | Microsoft (Maaden licences) | Included in Azure | Per SoW 3.4.4
11 | Azure Databricks (or Snowflake) | Data Platform | P2 onwards | AI/ML pipelines, big data | Microsoft (Maaden pays) | USD 5-10K / month
12 | Vector DB (Pinecone, Weaviate, Azure Cognitive Search) | AI Infrastructure | P2 onwards | Embeddings for AI agent RAG | Various (Maaden pays) | USD 500-2K / month
13 | Anthropic Claude API | AI/LLM | P2 onwards | Primary LLM for AI agents (Progress Verification, RFI, Schedule) | Anthropic (Maaden pays) | USD 3-5K / month | Direct API - Maaden procurement
14 | Azure OpenAI Service | AI/LLM | P2 onwards | Backup LLM, embeddings | Microsoft (Maaden pays) | USD 1-3K / month
15 | HuggingFace Inference Endpoints | AI/ML | P2 onwards | Custom fine-tuned models (KSA Arabic if needed) | HuggingFace (Maaden pays) | USD 500-1K / month
16 | MLflow | AI/ML Ops | P2 onwards | Model versioning + experiment tracking | Open source (XDH deploys) | Free | Self-hosted
17 | Oracle Aconex | Doc Management | All | Existing Maaden CDE for documents (integrate to) | Oracle (Maaden owns) | Existing | API integration
18 | Primavera P6 EPPM | Scheduling | All | Existing Maaden project schedules (integrate to) | Oracle (Maaden owns) | Existing | API integration
19 | SAP S/4HANA | ERP | All | Materials, Procurement, PS (integrate to) | SAP (Maaden owns) | Existing | OData API integration
20 | AVEVA PI System | Real-time Data | All | Historian, real-time process data (integrate to) | AVEVA (Maaden owns) | Existing | PI API integration
21 | Microsoft EPM System | PM Portfolio | All | Existing Maaden portfolio management (integrate to) | Microsoft (Maaden owns) | Existing | EPM API
22 | Microsoft Azure AD + ADFS | Identity | All | SSO for all users | Microsoft (Maaden owns) | Existing | SAML/OIDC integration
23 | Autodesk Navisworks + Revit + Plant 3D | BIM/CAD | M1 build | Federated 3D model viewer inputs (per SoW 3.1) | Autodesk (Maaden licences) | Existing | Model ingestion
24 | Autodesk APS / Forge Viewer | BIM/CAD | M1 build | Web-based 3D model viewer | Autodesk (Maaden pays) | USD 1-2K / month | Per active model
25 | IFC.js / xeokit SDK | BIM/CAD | M1 build | Custom 3D viewer (alt to Forge) | Open source | Free | Alt to Forge
26 | Figma | UI Design | All | Wireframes, style guide, prototypes | Figma (XDH provides) | USD 15/user/mo | For UI/UX work
27 | Miro / Mural | Collaboration | P1 | Requirements workshops, journey maps | Miro (XDH provides) | USD 10/user/mo
28 | Node.js + TypeScript | Runtime | All | Backend services | Open source | Free
29 | React + Next.js + Tailwind CSS | Frontend | All | Web UI framework | Open source | Free
30 | React Native + Expo | Mobile | M3 build | Mobile app for field verification | Open source | Free | iOS + Android
31 | Playwright / Cypress | Testing | All | End-to-end + integration testing | Open source | Free
32 | JMeter + K6 | Performance | P2 onwards | Load and performance testing | Open source | Free
33 | TestRail (Cloud) | Test Mgmt | P2 onwards | Test case + UAT script management | Gurock (XDH provides) | USD 40/user/mo
34 | Datadog (or Azure App Insights) | APM | All | Application monitoring, tracing, logging | Datadog (Maaden pays) | USD 3-5K / month
35 | PagerDuty | Incident Mgmt | P4+ | On-call rotation, alert routing | PagerDuty (Maaden pays) | USD 500 / month
36 | Azure Sentinel (or Splunk) | SIEM | All | Security event monitoring per NCA ECC | Microsoft (Maaden pays) | USD 5-10K / month | Per SoW 3.4.4
37 | Burp Suite Enterprise | Security | P2 onwards | Pen testing | PortSwigger (external firm) | One-off external
38 | OWASP ZAP | Security | P2 onwards | Automated security scans | Open source | Free
39 | Docebo (or Cornerstone) | LMS | P3+ | User training delivery, quizzes, certification | Docebo (Maaden pays) | USD 5-10K / year
40 | Postman + Swagger | API Testing | All | API contract dev + testing | Postman (XDH provides) | USD 15/user/mo

## Hardware & Infra
Hardware & Infrastructure
KSA in-Kingdom hosting mandatory per SoW 4.2. Endpoints, mobile devices, dev workstations.
# | Item | Specification | Quantity | Owner | Notes
1 | Azure Riyadh region tenancy | Sovereign cloud with data residency in KSA | 1 tenant | Maaden ICT | Primary hosting per SoW 4.2 + CST CCRF
2 | App Service Plan (Premium P3v3) | 4 vCPU, 16 GB RAM per instance x 3 instances (HA) | 3 instances | Maaden Azure sub | Web app tier
3 | Azure SQL Database (Business Critical) | Gen5, 16 vCores, 128 GB, geo-redundant | 2 DBs (Prod + DR) | Maaden Azure sub | Prod DB + DR pair
4 | Azure Databricks (Premium) | 8 x Standard_DS5_v2 workers, 32 vCPU each | 1 workspace | Maaden Azure sub | AI/ML training + inference
5 | GPU Node (NVIDIA A100 or H100) | For AI agent inference at scale | 1 node | Maaden Azure sub | On-demand
6 | Azure Storage Account (Premium) | Blob + File shares for documents, models, MC Dossiers | 1 account | Maaden Azure sub | Includes lifecycle policies
7 | Azure Cache for Redis (Premium) | 6 GB, geo-replicated | 1 cache | Maaden Azure sub | Session + caching
8 | Azure Application Gateway + WAF | v2 SKU with WAF policy per NCA ECC | 1 gateway | Maaden Azure sub | Front door + WAF
9 | Azure Firewall + Private Link | Central firewall, endpoints for SQL/Storage | 1 hub | Maaden Azure sub | Zero Trust posture
10 | Azure Sentinel | SIEM per NCA ECC requirement | 1 workspace | Maaden Azure sub | Log ingestion 100+ GB/day
11 | Azure Backup + Site Recovery | Automated backups + DR failover to Jeddah region | 1 vault | Maaden Azure sub | RPO 15 min, RTO 4 hours
12 | XDH Developer Workstations | MacBook Pro M3 32GB (dev) or Windows equiv | 7 units | XDH provides | 1 per team member
13 | iOS Test Devices | iPad Pro 12.9" (for M3 mobile app testing) | 3 units | XDH provides | For mobile UAT
14 | Android Test Devices | Samsung Galaxy Tab S9 Ultra + rugged tablets | 3 units | XDH provides
15 | Field Mobile Devices (Maaden operators) | Rugged Android tablets (Zebra ET80 or similar) | 200+ units | Maaden procurement | For M2/M3 mobile users
16 | RFID / QR scanning peripherals | For tagged equipment identification | 50+ units | Maaden procurement | M1 tag scanning
17 | Maaden Onsite Office (Ar Rjum) | Desk + secure network drop for XDH resource | 1-2 seats | Maaden provides | Per SoW 3.4.6 onsite req
18 | MFA Tokens / YubiKeys | Hardware MFA per NCA ECC | 7 tokens | Maaden ICT | For XDH team access
19 | VPN / SASE Client | Zscaler or Palo Alto Prisma per Maaden std | 7 licences | Maaden ICT | For XDH team access to Maaden network
20 | Video / Meeting Room | Maaden VC room for kickoff + gate reviews | As needed | Maaden provides | For workshops + reviews

## Integrations Register
Enterprise Integrations Register
All 8 enterprise systems + protocols. Owner = XDH Solution Architect unless flagged.
# | System | Vendor | Protocol | Data flow | Direction | Phase built | Auth | Access request
1 | Aconex | Oracle | REST API + Webhooks | Document metadata, transmittals, comments, approvals | Bidirectional | P1 design, P2 build | OAuth 2.0 | Maaden Aconex admin
2 | Primavera P6 EPPM | Oracle | XML/API + Database view | Schedules (baseline + current), WBS, calendars, resources, logic | Read (initial), Write (progress) | P1 design, P2 build | Named user credential | Maaden P6 admin
3 | SAP S/4HANA | SAP | OData v4 + SAP PI/PO | Materials Master, PO, PS work breakdown, GR, Invoices | Bidirectional | P2 build | OAuth 2.0 (SAP Cloud Connector) | Maaden SAP Basis
4 | AVEVA PI System | AVEVA | PI Web API + AF SDK | Tag data (real-time historian), asset framework | Read | P2 build | Windows Auth or Cert | Maaden AVEVA admin
5 | Microsoft EPM | Microsoft | CSOM + Project Server REST API | Portfolio projects, resource pool, timesheets | Bidirectional | P2 build | Azure AD SSO | Maaden Project admin
6 | Azure AD (Microsoft Entra ID) | Microsoft | SAML 2.0 + OIDC | User authentication, group membership, MFA | Read | P1 build | Service principal | Maaden IAM team
7 | ADFS (on-premise) | Microsoft | SAML 2.0 | Federation for legacy Maaden AD users | Read | P1 build | ADFS trust | Maaden IAM team
8 | SIEM (Azure Sentinel / Splunk) | Microsoft | Log Analytics HTTP Collector API | Application logs, audit events, security signals | Write (from platform) | P1 build | API key + endpoint auth | Maaden SOC
9 | Microsoft Outlook / Exchange Online | Microsoft | Graph API | Email notifications, calendar invites | Write | P2 build | Azure AD delegated | Maaden IAM team
10 | ServiceNow (Maaden ITSM) | ServiceNow | REST API | Incident tickets from platform, change requests | Write | P4 build | OAuth 2.0 | Maaden ITSM admin

## KSA Compliance
KSA Compliance Checklist
NCA ECC-1:2018 cybersecurity, PDPL data privacy, CST CCRF cloud, ISO 27001. Owner: KSA Compliance / Security Lead.
# | Regulation | Requirement | Evidence Type | Due Week | Owner | Status
1 | NCA ECC-1:2018 | Establish Cybersecurity Governance Framework | Policy documents | W2 | KSA Security | Not started
2 | NCA ECC-1:2018 | Asset management + classification (all data assets categorised) | Asset register | W3 | KSA Security + DBA | Not started
3 | NCA ECC-1:2018 | Access control per least privilege + MFA for privileged accounts | IAM policy + config | W3 | KSA Security + Sol Arch | Not started
4 | NCA ECC-1:2018 | Encryption at rest (AES-256) + in transit (TLS 1.3) | Config screenshots + attestation | W4 | KSA Security + DBA | Not started
5 | NCA ECC-1:2018 | Vulnerability management + monthly patching | Patch log + vuln scan reports | W4 baseline, ongoing | KSA Security + DBA | Not started
6 | NCA ECC-1:2018 | SIEM integration + 24/7 monitoring | SIEM config + SOC contract | W3 | KSA Security | Not started
7 | NCA ECC-1:2018 | Incident Response Plan (IR playbooks + RACI) | IRP document + tabletop | W6 | KSA Security | Not started
8 | NCA ECC-1:2018 | Business Continuity + DR (RTO 4h, RPO 15 min) | DR runbook + DR test evidence | W16 | KSA Security + DBA | Not started
9 | NCA ECC-1:2018 | External penetration test annually | Pen test report (external firm) | W14-15 | KSA Security + external | Not started
10 | NCA ECC-1:2018 | Cybersecurity awareness training for all users | Training records | W15+ | KSA Security + PM | Not started
11 | PDPL (Personal Data Protection Law) | Data Protection Officer (DPO) nominated at Maaden | DPO nomination letter | W1 | Maaden DPO | Not started
12 | PDPL | Data Privacy Impact Assessment (DPIA) for platform | DPIA report | W3 | KSA Security + Doc Ctrl | Not started
13 | PDPL | Data classification (personal, sensitive personal, non-personal) | Data classification matrix | W3 | KSA Security + Doc Ctrl | Not started
14 | PDPL | Consent management (where personal data collected) | Consent flows + UX | W6 | KSA Security + Sol Arch | Not started
15 | PDPL | Data subject rights (access, rectification, erasure) implemented | DSR workflows | W12 | KSA Security + Sol Arch | Not started
16 | PDPL | Cross-border data transfer controls | Data flow map + attestation | W3 | KSA Security | Not started
17 | PDPL | Data retention + deletion policy | Retention schedule + tech control | W6 | KSA Security + DBA | Not started
18 | PDPL | Annual PDPL attestation | Signed attestation letter | Y2 onwards | KSA Security | Not started
19 | CST CCRF (Cloud Computing Regulatory Framework) | In-Kingdom hosting confirmed (Azure Riyadh region) | Azure region confirmation | W1 | KSA Security + DBA | Not started
20 | CST CCRF | CST Level classification (L1 to L4) determined + hosted appropriately | CST classification memo | W2 | KSA Security | Not started
21 | CST CCRF | Cloud vendor operational + physical controls documented | Cloud vendor attestation | W3 | KSA Security | Not started
22 | CST CCRF | Data sovereignty (never leaves KSA except with CST approval) | Data residency matrix | W3 | KSA Security | Not started
23 | ISO 27001 | ISMS baseline + statement of applicability | ISMS documentation | W6-8 | KSA Security | Not started
24 | ISO 27001 | Pre-audit + gap assessment (external) | Pre-audit report | W30-32 | KSA Security + external | Not started
25 | ISO 27001 | Full certification audit (Y2) | ISO 27001 certificate | Y2 | KSA Security + external | Not started

## Deliverables Register
Deliverables Register (per SoW 3.4.5)
Every deliverable with acceptance criteria and payment triggers.
# | Deliverable | Type | Due Week | Acceptance Criteria | Owner | Phase | Payment Trigger?
1 | BIM Execution Plan (BEP) v1.0 | Document | W4 | Signed off by Maaden PMO. Covers all 5 modules, roles, standards. | Programme Manager | P1 | Yes (G1)
2 | Requirements Document v1.0 (5 modules) | Document | W4 | Signed off by Maaden PMO. All functional + non-functional requirements captured. | Solution Architect + Module | P1 | Yes (G1)
3 | Solution Architecture v1.0 | Document | W4 | Internal review + Maaden ICT review. Includes integration approach. | Solution Architect | P1 | Yes (G1)
4 | KSA Cloud Environment (Dev, UAT, Perf) | Infrastructure | W4 | Environments live in Azure Riyadh. Sanity tests pass. | DBA + KSA Security | P1 | Yes (G1)
5 | NCA ECC Gap Assessment v1.0 | Document | W4 | Baseline gap analysis complete. Remediation plan attached. | KSA Security | P1 | Yes (G1)
6 | PDPL DPIA v1.0 | Document | W4 | DPIA submitted to Maaden DPO. | KSA Security + Doc Ctrl | P1 | Yes (G1)
7 | M2 AWP Pilot Application | Software | W12 | Live in Prod for selected ARGP area. UAT scripts pass 95%+. | Sol Architect + Module | P2 | Yes (G2)
8 | M3 Pre-Comm + MC Pilot Application | Software | W12 | Live in Prod for selected ARGP area. UAT scripts pass 95%+. | Sol Architect + Module | P2 | Yes (G2)
9 | AI Agents (Progress, RFI, Schedule, Punch List) | Software | W12 | 4 AI agents live per SoW 3.3.4. Baseline accuracy >70%. | AI/ML Engineer | P2 | Yes (G2)
10 | Enterprise Integrations (Aconex, P6, SAP, AVEVA, EPM) | Software | W12 | Integration test report. Round-trip data flows verified. | Solution Architect | P2 | Yes (G2)
11 | External Pen Test Report v1.0 | Document | W15 | Third-party report. All Critical + High closed. | KSA Security + ext | P2/P3
12 | Pilot Acceptance Memo (G3) | Document | W16 | Signed off by Maaden PMO after pilot validation. | PM + Maaden PMO | P3 | Yes (G3)
13 | KPI Dashboards v1.0 | Software | W13 | Live dashboards covering 8 SoW KPIs. | AI/ML Engineer | P3
14 | User Training - Super Users | Training | W11-13 | Training deck + certification quiz. 90%+ pass rate. | Module + PM | P2/P3
15 | User Training - End Users (~500 people) | Training | W36 | Training delivered. Attendance + quiz records. | Module + PM | P4
16 | M1 CDE Full Application (Federated Viewer, Doc Mgmt, P&ID, MDR) | Software | W24 | Live in Prod for all users. Performance SLA met. | Sol Architect + Module | P4 | Yes (G4)
17 | M4 Quality Full Application | Software | W29 | Live in Prod for all users. UAT complete. | Module + Sol Architect | P4 | Yes (G5)
18 | M5 Procurement + Supply Chain Full Application | Software | W32 | Live in Prod. SAP round-trip verified. | Module + Sol Architect | P4 | Yes (G6)
19 | User Manual v1.0 | Document | W38 | For sales reps + end users. Signed off by Doc Ctrl. | Doc Controller | P4
20 | Admin Manual v1.0 | Document | W38 | For content editors + Maaden ICT. | Doc Controller | P4
21 | Technical Documentation Pack | Document | W38 | For future dev handoff. Architecture, API, runbooks. | Sol Architect + DBA | P4
22 | Operational Runbooks (10+) | Document | W39 | Backup, patching, DR failover, incident response, upgrade. | DBA + KSA Security | P4
23 | Knowledge Transfer to Maaden ICT Support | Training | W39 | L1/L2/L3 handover complete. ICT sign-off. | Sol Architect + DBA | P4
24 | ISO 27001 Pre-Audit Report | Document | W32 | External pre-audit. Findings actionable. | KSA Security + ext | P4
25 | Final Acceptance Certificate (G6) | Document | W40 | Signed by Maaden CFO/CIO. End of Year 1 build. | PM + Maaden CFO/CIO | P4 | Yes (G6)

## Quality Gates
Quality Gates + Payment Milestones
6 gates aligned with SoW 3.3.10 phases. Payment released at each gate sign-off.
Gate | Title | Week | Acceptance Criteria | Payment % | Sign-off Authority
G1 | Requirements Sign-off | W4 | BEP v1.0 signed ¦ Requirements v1.0 signed ¦ Solution Arch v1.0 ¦ Environments live ¦ NCA ECC baseline ¦ PDPL DPIA v1.0 | 15% | Maaden PMO
G2 | Pilot UAT + Integration | W12 | M2 AWP Pilot live ¦ M3 Pre-Comm Pilot live ¦ 4 AI Agents live ¦ Enterprise integrations verified ¦ Pen test complete | 20% | Maaden PMO
G3 | Pilot Acceptance | W16 | Pilot validated in production for selected ARGP area ¦ KPIs baselined ¦ Super-user training complete ¦ Defects closed | 15% | Maaden PMO
G4 | M1 + M2/M3 Full Live | W24 | M1 CDE full live (Federated Viewer, Doc Mgmt, P&ID, MDR) ¦ M2/M3 rolled to all ARGP users ¦ Performance SLA met at 500+ concurrent users | 15% | Maaden PMO
G5 | M4 Quality Full Live | W29 | M4 Quality full live (NCR, ITP, NDT, welding QA) ¦ Field test complete ¦ ISO 27001 pre-audit initiated | 15% | Maaden PMO
G6 | M5 Procurement Live + Final Acceptance | W40 | M5 Procurement full live ¦ SAP round-trip verified ¦ User training rollout complete ¦ Doc pack + runbooks ¦ ICT handover ¦ ISO 27001 pre-audit passed | 20% | Maaden CFO + CIO
TOTAL PAYMENT DISTRIBUTION
| Mobilisation on PO |  |  | 5%
| G1 |  |  | 15%
| G2 |  |  | 20%
| G3 |  |  | 15%
| G4 |  |  | 15%
| G5 |  |  | 15%
| G6 |  |  | 15%
| Final acceptance handover |  |  | 5%
| TOTAL |  |  | 100%

## Risk Register
Risk Register - Top 25 Risks
Reviewed weekly at internal standup. Reviewed monthly with Maaden PMO.
# | Risk | Likelihood (1-5) | Impact (1-5) | Score | Mitigation | Owner | Status
1 | KSA cloud tenancy delays (Azure Riyadh provisioning >2 weeks) | 4 | 5 | 20 | Request tenancy Day 1. Escalate to Microsoft Riyadh account team. Have Oracle/STC as fallback. | KSA Security + DBA | Open
2 | Enterprise system access delays (Aconex, P6, SAP, AVEVA credentials) | 5 | 4 | 20 | Raise access requests Day 1 with ITSM. Weekly follow-up. Escalate to Maaden PMO if >2 weeks. | Sol Architect + PM | Open
3 | NCA ECC audit findings delaying go-live | 3 | 5 | 15 | Bring KSA Security in Day 1. Baseline in W2. External pre-audit in W14-15 before pilot go-live. | KSA Security | Open
4 | AI agent accuracy below Maaden expectations | 3 | 4 | 12 | Set clear success criteria in W2. Baseline metrics in W6. Iterate with Maaden SMEs. | AI/ML Engineer | Open
5 | Change of Maaden PMO stakeholder or requirements late in build | 4 | 4 | 16 | Signed BEP v1.0 in W4 as scope baseline. Change control per T&C Section 4. Escalate to Steering. | PM | Open
6 | Enterprise integration API changes mid-build (Aconex, SAP updates) | 2 | 4 | 8 | Version pin API contracts. Monitor vendor release notes. Have fallback plan (manual sync). | Sol Architect | Open
7 | KSA Ramadan / Hajj holidays impact velocity in Q1/Q2 | 5 | 3 | 15 | Plan sprints around Islamic calendar. Set expectations up front with team + Maaden. | PM | Open
8 | Pen test finds critical vulnerabilities blocking pilot | 3 | 5 | 15 | Continuous security testing during build. External pen test in W14 gives buffer to fix by W16. | KSA Security | Open
9 | Team member unavailability (illness, resignation) | 3 | 3 | 9 | Documentation as we go. Knowledge sharing every sprint. Cross-training for critical roles. | PM | Open
10 | AI LLM API cost overrun (Anthropic Claude usage exceeds budget) | 3 | 3 | 9 | Monitor API spend weekly. Implement caching + prompt optimisation. Set spend alerts. | AI/ML Engineer | Open
11 | ARGP site logistics delays (badges, HSE induction, workstations) | 3 | 3 | 9 | Start onboarding process W1. Send required docs in advance. Have contingency for remote work. | PM + KSA Security | Open
12 | User adoption below targets (M2 AWP <50% daily active) | 3 | 4 | 12 | Super user champions in W11-13. Regular user forums. Executive sponsorship communication. | PM + Module | Open
13 | Data quality issues in Maaden source systems (dirty data) | 4 | 3 | 12 | Data profiling in W2. Automated cleansing rules. Set quality thresholds with Maaden. | DBA + Module | Open
14 | SAP integration complexity underestimated (custom fields, BADIs) | 3 | 4 | 12 | Deep-dive discovery with Maaden SAP Basis in W1. External SAP consultant on call. | Sol Architect | Open
15 | Performance issues at 500+ concurrent users | 2 | 4 | 8 | Perf testing in W10 pilot. Scale Azure App Service Plan tiers. Redis caching in place. | DBA + Sol Architect | Open
16 | Mobile app connectivity issues at Ar Rjum site (remote area) | 3 | 3 | 9 | Offline-first design. Sync when connectivity available. Cache on device. | Sol Architect + Module | Open
17 | DR (disaster recovery) test fails | 2 | 4 | 8 | Monthly DR test drill starting W20. Automated failover playbooks. | DBA + KSA Security | Open
18 | AVEVA PI data volumes overwhelm platform (millions of tags) | 3 | 3 | 9 | Tag-level filtering at PI edge. Aggregate before ingestion. Time-series DB (InfluxDB) if needed. | Sol Architect + DBA | Open
19 | Vendor lock-in concerns from Maaden | 2 | 3 | 6 | Open APIs. Exit strategy documented. IP transfer per T&C Section 8. | PM + Sol Architect | Open
20 | Language localisation ask late (Arabic UI) | 3 | 3 | 9 | Design UI framework with i18n from Day 1. Confirm scope with Maaden in W1. | Sol Architect + Module | Open
21 | Regulatory change during build (NCA ECC-2, PDPL update) | 2 | 4 | 8 | Monitor NCA + SDAIA publications. Have compliance sprint reserve. Escalate to Maaden. | KSA Security | Open
22 | AI model bias or hallucinations impact Maaden decision-making | 2 | 5 | 10 | Human-in-the-loop for AI outputs. Confidence scoring. Regular model evaluation. | AI/ML Engineer | Open
23 | Late-stage scope additions ("could you also add...") | 4 | 3 | 12 | Firm change control from W1. Every ask logged, priced, decisioned via Change Request. | PM | Open
24 | Cybersecurity incident during build | 2 | 5 | 10 | IR playbook in place from W6. 24/7 SOC via SIEM. Tabletop exercise before pilot. | KSA Security | Open
25 | End of Year 1 handover to Maaden ICT delayed / rejected | 2 | 4 | 8 | Involve Maaden ICT from Day 1. Weekly shadow sessions. ICT sign-off at G4 + G5 + G6. | PM + Sol Architect | Open

## Maintenance Year 2-5
Year 2-5 Maintenance + Support Model
4 years of ongoing support post-handover. Linear escalation on maintenance cost.
# | Activity | Frequency | Team FTE | Description | Y2 Cost AED | Y3 Cost AED | Y4-Y5 Cost
1 | L1 Support (Tier 1 helpdesk) | Continuous | 0.5 FTE PM + Module | First-line user support. Response 4h, resolution 24h. | 200000 | 210000 | 220000
2 | L2 Support (Tier 2 technical) | Continuous | 0.3 FTE Sol Architect + DBA | Second-line: bug diagnosis, config, minor fixes. | 130000 | 137000 | 143000
3 | L3 Support (Tier 3 developer escalation) | On demand | 0.2 FTE Sol Architect + AI/ML | Third-line: code changes for critical bugs. | 90000 | 95000 | 100000
4 | Quarterly Patches + Minor Releases | Quarterly | DBA + Sol Architect | 4 patch releases per year. Security updates, minor features. | 60000 | 63000 | 66000
5 | Feature Enhancements (5% of build cost) | Rolling | Sol Architect + Module | Top 10 backlog items per year. Prioritised with Maaden PMO. | 100000 | 105000 | 110000
6 | Annual NCA ECC Audit | Annual | KSA Security | External auditor engagement. Findings remediation. | 30000 | 32000 | 34000
7 | Annual PDPL Attestation | Annual | KSA Security + Doc Ctrl | Attestation letter submitted to SDAIA. | 15000 | 16000 | 17000
8 | Annual DR Test | Annual | DBA + KSA Security | Full failover test to Jeddah region. | 20000 | 21000 | 22000
9 | Pen Test (annual) | Annual | KSA Security + external | External pen test + remediation. | 40000 | 42000 | 44000
10 | Unreal / Stack Upgrades | Y3, Y5 | DBA + Sol Architect | Major version upgrades of platform stack. | 0 | 80000 | 80000
11 | Multi-tenant Expansion Support | Y2 onwards | Sol Architect | Onboard additional Maaden projects (Ma'aden Aluminium, Waad Al Shamal). | 50000 | 60000 | 70000
12 | Monthly Reporting + PMO Reviews | Monthly | 0.1 FTE PM | Monthly SLA report + steering committee meetings. | 30000 | 32000 | 34000
13 | Contingency / Buffer | As needed | Various | 10% contingency for unforeseen support work. | 40000 | 45000 | 50000
| ANNUAL TOTAL |  |  |  | 805000 | 938000 | 990000
SERVICE LEVEL AGREEMENT (SLA)
| Priority | Definition | Response Time | Resolution Time | Availability
| P1 (Critical) | Platform down / major security incident | 15 min | 4 hours | 24/7
| P2 (High) | Major feature broken, affects >50 users | 1 hour | 1 business day | Business hours + escalation
| P3 (Medium) | Minor feature bug, workaround available | 4 hours | 5 business days | Business hours
| P4 (Low) | Cosmetic or enhancement request | 1 business day | Next release | Business hours
5-YEAR TCO SUMMARY
Year | Description |  |  | AED |  |  | USD (at 3.6725)
Y1 | Build (per current XDH quote) |  |  | 4609905 |  |  | 1255250
Y2 | Maintenance (Y2 total) |  |  | 805000 |  |  | 219197
Y3 | Maintenance (Y3 total) |  |  | 938000 |  |  | 255412
Y4 | Maintenance (Y4 est) |  |  | 990000 |  |  | 269571
Y5 | Maintenance (Y5 est) |  |  | 990000 |  |  | 269571
5-YR TCO | Total 5-year cost of ownership |  |  | 8332905 |  |  | 2269001

## Meeting Cadence
Meeting Cadence + Communication Plan
Every scheduled interaction between XDH team and stakeholders.
# | Meeting | Frequency | Duration | Attendees | Purpose / Outputs
1 | Internal Daily Standup | Daily (Mon-Fri) | 15 min | All 7 XDH team | Yesterday, today, blockers. Async in Slack if remote.
2 | Sprint Planning | Every 2 weeks | 90 min | PM + Sol Architect + AI/ML + Module | Refine backlog, story points, sprint goal.
3 | Sprint Review + Demo | Every 2 weeks | 60 min | All XDH team + Maaden PMO invited | Show working software. Get feedback.
4 | Sprint Retrospective | Every 2 weeks | 60 min | All XDH team | What went well, what to improve.
5 | Weekly Client Status Call | Weekly (Mondays) | 30 min | PM + Maaden PMO | Progress update, upcoming week, risks/issues log.
6 | Monthly Steering Committee | Monthly (last Thursday) | 90 min | PM + Maaden CIO + Maaden PMO | Programme status, strategic decisions, budget review.
7 | Phase Gate Reviews (G1-G6) | Per Phase Gate | 2 hours | ALL XDH + Maaden PMO + Maaden CIO for G6 | Formal acceptance sign-off. Payment trigger.
8 | Security Sync | Weekly (Wednesdays) | 30 min | KSA Security + Maaden CISO/SOC | Security incidents, findings, patches, compliance status.
9 | Integration Working Group | Weekly (Thursdays) | 60 min | Sol Architect + Maaden system owners (Aconex, P6, SAP, AVEVA admins) | Integration progress, API changes, sandbox refreshes.
10 | AI/ML Model Review | Monthly | 60 min | AI/ML Engineer + Maaden SMEs | Model performance, bias check, prompt tuning, agent updates.
11 | User Forum (feedback) | Monthly (from Phase 3) | 60 min | PM + Module + 20 pilot users | User feedback, feature requests, pain points.
12 | Change Control Board (CCB) | As needed | 30 min | PM + Sol Architect + Maaden PMO | Review Change Requests. Approve/reject with pricing impact.
13 | Executive Briefing | Quarterly | 30 min | PM + Maaden CIO/CFO | Programme health, budget, milestones, strategic view.
14 | Compliance Audit Prep | Bi-annual (with audit cycle) | 2 hours | KSA Security + external auditor + Maaden CISO | NCA ECC, PDPL, ISO 27001 pre-audit rehearsal.
15 | Kickoff (Week 1) | Once (W1) | 2 hours | All + Maaden PMO + Maaden CIO | Programme kickoff, roles, communication plan, risks.
16 | Requirements Workshops (5) | W2-W4 (5 sessions) | 3 hours each | Module + Sol Architect + Maaden SMEs | One per module. Deep-dive functional requirements.
17 | Training Sessions | W11-W15 + W34-W38 | Variable | Module + PM + Maaden users | Super-users first, then end users, then ICT Support.
18 | Handover Session (Y1 close) | Once (W39-W40) | 3 hours | All XDH + Maaden ICT + Maaden PMO | Knowledge transfer for L1/L2/L3 support post-Year 1.