## Manpower Loading
Maaden ARGP Digitalization Platform - Manpower Deployment Schedule (per Phase, all roles)
Client: | Saudi Arabian Mining Company (Maaden) - ARGP affiliate
RFP Ref: | ARGP-DIGI-APP-SOW-001 Rev. 00 (02/04/2025)
Project Duration: | 12 months Year 1 (per SOW 3.3.10 Phase 1-4)
Prepared By: | XD House LLC FZ
Date / XDH Ref: | 2026.06.01 ¦ XDH-AE-Q26-05-00029
Phase / Service | Role | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | Phase Total | Notes / SOW reference
PHASE 1: REQUIREMENT FINALIZATION + SETUP + CORE CONFIG (W 1-4, M1)
Programme Mgmt | Programme Manager | 1 | [11 empty] | 1 | SOW 3.4.7 mandatory PM role Kick-off + relationship establishment, daily Maaden coordination
Solutioning | Solution Architect (Platform) & (Integration) | 1 | [11 empty] | 1 | SOW 3.4.7 Sr Functional/Technical - platform architecture lead Integration architecture design (light - kicks off in P2)
Database | Database Administrator | 0.5 | [11 empty] | 0.5 | SOW 3.4.7 mandatory Sr DBA - schema design start + KSA tenancy DB
Compliance | KSA Compliance / Security Lead | 1 | [11 empty] | 1 | SOW 3.4.4 - NCA ECC + PDPL + CCRF baseline, ISMS, AAD/ADFS SSO
Domain | Module Specialist | 1 | [11 empty] | 1 | Requirements + ARGP domain context for solution design
Doc Control | Documents Controller | 1 | [11 empty] | 1 | SOW 3.4.7 mandatory Document Controller
PHASE 1 PEAK FTE | [13 empty] | 5.5
PHASE 2: PILOT MODULE DEPLOYMENT ON SELECTED ARGP AREA (W 5-12, M2-M3)
Programme Mgmt | Programme Manager |  | 1 | 1 | [9 empty] | 2 | SOW 3.4.7 - phase 2 milestone delivery + Maaden steering
Solutioning | Solution Architect (Platform) & (Integration) |  | 1 | 1 | [9 empty] | 2 | Code reviews, technical decisions, platform IP design Integration architecture - Aconex + P6 inbound design Aconex CDE adapter + Primavera P6 sync + DCMA checks ADFS / MS EPM connector scaffolding
AI/ML | AI / ML Engineer (Lead) |  | 1 | 1 | [9 empty] | 2 | SOW 3.3.4 - 4 AI agents for M3 AWP (ingest + ontology + anomaly + KPI)
Database | Database Administrator |  | 1 | 1 | [9 empty] | 2 | SOW 3.4.7 - production schema, indexes, query optimization
Build Domain | Module Specialist |  | 1 | 1 | [9 empty] | 2 | SOW 3.3.4 M3 - AWP module code (data model + API + frontend) ARGP context + ISO 19650 alignment + AWP workflow design
Compliance | KSA Compliance / Security Lead |  | 0.5 | 0.5 | [9 empty] | 1 | Security review of pilot code + pen test prep
Onsite | KSA Onsite Account Manager |  | 1 | 1 | [9 empty] | 2 | Continuous onsite + Maaden workshop facilitation
Doc Control | Documents Controller |  | 1 | 1 | [9 empty] | 2 | SOW 3.4.7 - pilot deliverable doc control
PHASE 2 PEAK FTE | [13 empty] | 15 | Phase 2 FTE-mo: 22.0
PHASE 3: PILOT VALIDATION + KPI + TRAINING + FEEDBACK (W 13-16, M4)
Programme Mgmt | Programme Manager Training |  |  |  | 1 | [8 empty] | 1 | SOW 3.4.7 - Phase 3 gate management SOW 3.4.6 train-the-trainer + materials + user adoption Onsite training coordination + Phase 3 gate
Solutioning | Solution Architect (Platform) & (Integration) |  |  |  | 1 | [8 empty] | 1 | UAT support + defect triage + KPI tuning Integration UAT fixes
AI/ML | AI / ML Engineer |  |  |  | 1 | [8 empty] | 1 | AI agent KPI evaluation vs SOW Section 4 targets
Database | Database Administrator |  |  |  | 1 | [8 empty] | 1 | SOW 3.4.7 - performance tuning based on pilot load
Build Domain | Module Specialist |  |  |  | 1 | [8 empty] | 1 | Pilot module remediation backlog UAT facilitation + CDE workflow validation
Compliance | KSA Compliance / Security Lead |  |  |  | 0.5 | [8 empty] | 0.5 | Compliance validation against NCA ECC
Doc Control | Documents Controller |  |  |  | 1 | [8 empty] | 1 | SOW 3.4.7 - Phase 3 acceptance + KPI report + training pack
PHASE 3 PEAK FTE | [13 empty] | 6.5
PHASE 4: FULL-SCALE ROLLOUT + M1+M2+M4+M5 BUILD + IP TRANSFER + HYPER-CARE (W 17-52, M5-M12)
Programme Mgmt | Programme Manager Training |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 8 | SOW 3.4.7 - full rollout management + Go-Live + IP handover Tapering: M5-M6 full, M7-M8 half, then handed to Maaden Continuous KSA presence + Go-Live + IP transfer signing
Solutioning | Solution Architect (Platform) & (Integration) |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 7 | Architecture oversight for M1+M2+M4+M5 build, ramps M11-M12 Production integration cutover (SAP + Aveva PI + full EPM/ALM/SIEM)
AI/ML | AI / ML Engineer |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 8 | SOW 3.3.4 - 4 additional AI agents for M1+M2+M4+M5
Database | Database Administrator |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 8 | SOW 3.4.7 - production DB tuning + backup + DR
Build Domain | Module Specialist |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 8 | Full SAP + Aveva PI integration build + production cutover Full MS EPM + ALM + SIEM integration build SOW 3.3.4 - build M1+M2+M4+M5 from scratch + onsite rollout Onsite ramp-up per affiliate area + BIM/CDE adoption
Compliance | KSA Compliance / Security Lead |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 8 | SOW 3.4.4 - NCA ECC compliance pass + security evidence + pen test
Doc Control | Documents Controller |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 8 | SOW 3.4.7 - Go-Live evidence + Final Acceptance + IP transfer docs
PHASE 4 PEAK FTE | [13 empty] | 55
MONTHLY HUMAN FTE TOTAL (all phases summed) |  | 5.5 | 7.5 | 7.5 | 6.5 | 7 | 7 | 7 | 7 | 7 | 7 | 6.5 | 6.5 | 82 | Total Year 1 FTE-months
Notes:
1. Per-phase view: each phase block lists ALL 13 roles active in that phase with FTE for each month. Same role appears in each phase block they cover (PM, Solution Architects, Sr DBA, BIM/AWP, KSA Security, Onsite AM, Doc Controller all span multiple phases).
2. SOW 3.4.7 mandatory roles present in every phase: Programme Manager + Solution Architect (Sr Functional/Technical) + Senior DBA + Documents Controller.
3. SOW 3.4.6 onsite presence in Ras Al-Khair (RAK): KSA Onsite Account Manager continuous M1-M12 + BIM/AWP Specialist onsite Phases 2/3/4 + Solution Architects onsite for kick-off/gates/rollout + Training Lead Phase 3.
4. Custom Build delivers Maaden ownership of all platform IP at Final Acceptance (W52). Source code + AI models + configurations + documentation transfer.
5. Year 2-5 Maintenance Team: 2.0 FTE shared pool covered by SAR 4.2M/yr maintenance fee (5% p.a. escalation). Maaden may terminate maintenance any anniversary.
6. Human FTE = senior consultant person-month at full-time equivalent (22 days/mo at 8 hrs/day).
7. All subscription costs (AI APIs, KSA hosting, GPU, vector DB, third-party software, hardware) EXCLUDED per Maaden direct procurement.