## Queries and Assuption
XDH Clarifications for SoW ARGP-DIGI-APP-SOW-001 Rev. 00
# | SoW Ref | Quesries | Description | XDH Assumption
1 | 3.4.6 | How many months should the project take to complete? | Maaden's SoW says "this project should complete within XX months" - Please confirm the duration | 12 months Year 1 implementation following the SoW 3.3.10 phase structure
2 | 3.3.10 | When does Phase 4 (Full Rollout) end? | The SoW says Phase 4 is "Weeks 17+" - Please confirm the expection duration of Phase 4. | Phase 4 = Weeks 17 to 52 (8 months) ending at Go-Live and Final Acceptance
3 | 3.1.9, 3.2.18, 3.3.10 | Which module timeline governs the overall programme? | The SoW gives DIFFERENT timelines for different modules. Module 1 and Module 2 say 8 weeks. Module 3 says 17+ weeks. Please confirm the Timeline to follow | Module 3 timeline (SoW 3.3.10) governs. Module 1 and 2 pilots run inside Phase 2 (Weeks 5-12)
4 | N/A | Please confirm master sequencing of all 5 modules across Year 1 and Year 2 | Each module has its own timeline section but they do not tie together. Please provide one overall plan showing what is live when. | Year 1: M1+M2+M3 pilot then production from W17, M4 Phase 1 baseline, M5 baseline only. Year 2: M2/M3 full production, M4 Phase 2, M5 production
5 | N/A | How many users will use the platform? | The SoW does NOT specify how many expected users. Please verify | 500 named users Year 1 (60 admin, 440 end users). 150 concurrent peak. 50% growth Year 2
6 | N/A | How much data will the system handle (documents, BIM models, point clouds)? | The SoW does NOT specify data volumes. 1 TB vs 100 TB requires very different storage and processing capacity, with massive cost difference. | 5 TB Year 1: 50K documents, 200 BIM models, 2 TB point clouds, 1 TB project data. Growth 30% p.a.
7 | 3.4.4 IT Security | Verify cloud provider in KSA. | The SoW says "must be hosted in KSA".Please verify the expected host (Azure Riyadh, Oracle Riyadh, STC Cloud, etc.) | Microsoft Azure Riyadh Region (primary) + Azure Jeddah (DR). Both KSA. Procured by Maaden direct
8 | 3.3.7 | What are the specific acceptance criteria for each deliverable (D1 to D7)? | The SoW lists 7 deliverables but does not specify the Criteria