## 1. Summary
MAADEN ARGP - COMMERCIAL RECONCILIATION (all AED, excl WHT/VAT unless stated)
Three internal versions exist. This workbook reconciles them. Prepared 2026-07-06.
| Quote Letter (00029, 01 Jun) | Pricing Calculator v2 (00030) | Master Roadmap (00030 v1.0, 02 Jul)
Year 1 build price | 2841125 | 9906699 | 4172335.6009
Year 1 manpower plan (FTE-months) | 33 | 83 | 77
Resource cost basis at card rates | 2712600 | 6342600 | 5907000
Implied margin at card rates | -9.798% | 26.37% | -62.81%
5-Year TCO (stated) | 4907333 |  | 8150000
Timeline | 52 weeks (12 mo) | 12 months | 40 weeks (10 mo)
Payment terms | 20/80/10 (sums to 110% - ERROR) | n/a | 8 tranches = 100%
KEY FINDINGS
1. Quote letter = 28.7% of its own pricing calculator, uniformly across all 4 phases. No documented discount rationale.
2. Calculator Phase 4 omits AI/ML Engineer + Security Lead prices (2 roles x 8 mo x 72,600 = 1,161,600 before uplifts). See sheet 2.
3. Calculator hardware line (15%) misses one resource row in EVERY phase. See sheet 2 corrected column.
4. Roadmap price (4.6M inc VAT+WHT) cannot cover its own 77 person-month plan at card rates (cost ~5.9M). See sheet 3.
5. Only the calculator at 9.9M covers its stated manpower with the stated 70% margin - but that is 3.5x the quoted price.
6. Quote payment terms sum to 110% (20+80+10). Roadmap has a correct 100% 8-tranche schedule - adopt it.
7. Terminology: calculator applies 5% "VAT", quote applies 5% "WHT". KSA VAT is 15%; cross-border WHT is 5%. Needs tax review (not tax advice - verify with advisor).
DECISION REQUIRED: pick ONE price basis, regenerate quote + roadmap from it, and archive the others.

## 2. Version Detail
YEAR 1 PHASE FEES BY VERSION (AED excl WHT)
Phase | Quote Letter | Calculator v2 (as-is) | Roadmap basis | Calculator CORRECTED | Corrected calc inputs | Resource sum/phase (P4 incl. 2 missing roles)
Phase 1 (W1-4) | 232687.5 | 813730.5 | not phase-split in deck | 832243.5 | 425700
Phase 2 (W5-12) | 625685 | 2195193 |  | 2232219 | 1141800
Phase 3 (W13-16) | 269832.5 | 955663.5 |  | 974176.5 | 498300
Phase 4 (W17+) | 1712920 | 5942112 |  | 8361144 | 4276800
Year 1 total | 2841125 | 9906699 | 4600000 | 12399783
Note: Roadmap 4.6M stated as inc VAT+WHT; others excl.
Reference totals (used by Summary) | 2841125 | 9906699 | 4172335.6009
Roadmap 4.6M back-calculated to excl-tax basis: |  |  |  |  | 15% | HW+Licences % (per calculator)
less 5% WHT then 5% VAT (as XDH applies them) |  |  |  |  | 70% | Margin % (per calculator)
Net-of-tax roadmap build fee | 4172335.6009
CALCULATOR ERRORS FOUND
P4: AI/ML Engineer row - Count 1, Months 8, Price BLANK (formula deleted). Missing 580,800.
P4: KSA Security Lead row - Count 1, Months 8, Price BLANK. Missing 580,800.
All phases: Hardware = 15% x (resource sum MINUS one row). P1 evidence: 52,965 = 15% x (425,700 - 72,600).
Sheet "Year 1 Total" contains an abandoned older rate table (33K/22K/19K roles, all zero) - delete to avoid confusion.
One calculator sheet still dated 2026.03.05.

## 3. Margin Analysis
MARGIN AT CARD RATES vs INTERNAL COST SCENARIOS (AED)
Card rates: PM 99,000/mo; all other roles 72,600/mo (source: calculator Sheet1 rate card, 22 days/mo).
| Quote (33 FTE-mo) | Calculator (83 FTE-mo) | Roadmap (77 FTE-mo)
PM months / other months | 12 / 21 | 12 / 71 | 12 / 65
Resource cost at card rates | 2712600 | 6342600 | 5907000
+ HW & licences 15% | 3119490 | 7293990 | 6793050
Year 1 price (excl tax) | 2841125 | 9906699 | 4172335.6009
Surplus / (shortfall) vs cost+HW | -278365 | 2612709 | -2620714.3991
Implied margin % on price | -9.798% | 26.37% | -62.81%
ASSUMPTIONS (edit blue cells)
PM rate /mo | 99000
Other role rate /mo | 72600
Internal cost ratio (cost as % of card rate) | 60%
SENSITIVITY: margin if card rates are SELL and true cost = ratio above
| Quote | Calculator | Roadmap
True delivery cost (resources x ratio + HW 15%) | 1871694 | 4376394 | 4075830
Margin % at true cost | 34.12% | 55.82% | 2.313%
READ: even at 60% cost ratio, check whether the quote covers the ROADMAP manpower plan - the quote prices the lean 33 FTE-mo plan only.

## 4. Recommendation
RECOMMENDED PATH TO ONE PRICE
1 | Fix the calculator: restore P4 AI/ML + Security formulas; fix HW range to full resource sum. Corrected total appears in Sheet 2 col E.
2 | Decide the manpower truth: roadmap 77 person-months is the delivery plan management approved - price against IT, not the 33 FTE-mo lean view.
3 | Set margin policy explicitly (calculator says 70%, briefing says 35%, roadmap says 40%). One number, documented.
4 | Regenerate the quote letter from the corrected calculator. Fix payment terms to the roadmap 8-tranche schedule (sums to 100%).
5 | Get tax treatment verified (5% WHT vs KSA 15% VAT reverse-charge; UAE entity invoicing KSA client). Flag: not tax advice - confirm with advisor.
6 | Version control: put the final numbers in ONE file; mark superseded files as ARCHIVED in the filename.