## Slide 1
MAADEN ARGP
Digitalization Platform
Internal Management Briefing
What we are bidding for, who the client is, the scope, the team, the timeline, and the price
XD House LLC FZ | Ref XDH-AE-Q26-05-00029 | June 2026
CLASSIFICATION: INTERNAL - For XDH Management Review

## Slide 2
Executive Summary
In one slide - what is this opportunity?
CLIENT
Maaden
Saudi Arabian Mining Company (KSA national flagship)
PROJECT
ARGP
Ar Rjum Gold Project - greenfield mining megaproject
YEAR 1 PRICE
AED 2.98M
AUD 1.1M / USD 812K (incl WHT)
5-YEAR TCO
AED 4.91M
Y1 + 4 years maintenance
WHAT WE ARE BIDDING FOR
Design, build, deploy and hand over a custom Digitalization Platform for the ARGP gold project - a 12-month engagement covering 5 functional modules + AI agents + KSA in-Kingdom hosting + 24/7 SLA.
WHY THIS MATTERS
1
Strategic Win
First major KSA enterprise platform deal. Opens door to Aramco, SABIC, ADNOC follow-ons.
2
Low Y1 Cash
AED 2.98M Y1 vs incumbents at AED 80-150M - we win on price + flexibility.
3
Tight Margin
35% gross margin. Manage scope creep tightly via Variation Clause 4.

## Slide 3
The Client and the Project
Who is Maaden and what is ARGP?
THE CLIENT - MAADEN
Saudi Arabian Mining Company
Publicly traded - HQ Riyadh, KSA
Largest mining company in Middle East
Government-aligned (PIF-owned majority)
Saudi Vision 2030 cornerstone enterprise
Affiliates (this scope: ARGP only):
- Maaden Aluminium
- Maaden Phosphate Company (MPC)
- Ar Rjum Gold Project (ARGP)
- Multiple gold & industrial operations
THE PROJECT - ARGP
Ar Rjum Gold Project
Flagship greenfield gold mining + processing
Multi-year mining megaproject (Ras Al-Khair)
Scale: USD-billions project budget
Vision 2030: local content + supply chain
What Maaden tendered:
SoW: ARGP-DIGI-APP-SOW-001 Rev. 00
Date: 02 April 2025
AI-powered enterprise platform
KSA in-Kingdom data residency required
Note: ARGP is the first affiliate. Multi-affiliate rollout is excluded from this scope (variation per affiliate).

## Slide 4
What Maaden Is Asking For
5 functional modules + AI capabilities + KSA hosting + compliance
M1
Engineering & Design Management
CDE + AI design checks + Digital Twin + 20 disciplines + Aconex integration
M2
Schedule Management & Project Controls
Primavera P6 + QSRA + EVMS + AWP + look-ahead
M3
Construction & Pre-Commissioning
8 sub-modules + AWP + Punch List + Pre-Comm + Computer Vision
M4
Quality Management & Assurance
Digital ITPs + NCR + CAPA + supplier scorecards + AI predictive quality
M5
Procurement & Supply Chain
PO + Material Traceability + EAC + integrated with ERP
CROSS-CUTTING
AI / ML Engine
Predictive analytics, CV, QSRA
KSA In-Kingdom Hosting
Azure Riyadh / Oracle KSA
Compliance
NCA ECC + PDPL + CCRF + ISO
WHY THIS PROPOSAL IS COMPLEX
- 5 separate modules each with their own SoW sections (3.1, 3.2, 3.3, 3.4, 3.5)
- Mandates AI capabilities (predictive analytics, CV, Digital Twin, QSRA)
- Mandates KSA data residency + integration with 6+ Maaden enterprise systems (Aconex, P6, SAP, Aveva PI, MS EPM, ADFS, SIEM)
- 4-phase delivery with gate reviews at Weeks 4, 12, 16, 52

## Slide 5
Our Delivery Approach
4 phases over 12 months per SoW 3.3.10 + ongoing Year 2-5 maintenance
PHASE 1
W 1-4
Setup & Mobilisation
- Project kickoff - BIM Execution Plan - KSA tenant on Maaden cloud - Maaden AAD / ADFS SSO setup - NCA ECC + PDPL baseline - Architecture design - Requirements workshops
AED 232.7K
PHASE 2
W 5-12
Pilot Module Deployment
- Module 3 AWP pilot build - 4 AI agents (ingest, ontology, anomaly, KPI synthesiser) - Aconex + P6 integrations - 5 pilot dashboards - Test pack + UAT prep
AED 625.7K
PHASE 3
W 13-16
Pilot Validation + Training
- UAT on Maaden data - KPI measurement vs targets - Defect triage + fixes - Train-the-trainer (8 modules) - Phase 3 acceptance gate
AED 269.8K
PHASE 4
W 17-52
Full Rollout + IP Transfer
- Build Modules M1, M2, M4, M5 - SAP + Aveva PI + EPM integration - Multi-area ARGP rollout - Security hardening + audit - Go-Live + Final Acceptance - 1-month hyper-care
AED 1.71M
YEAR 2-5: ANNUAL MAINTENANCE & SUPPORT
Annual maintenance fee = 15% of build cost base, escalated 5% per year
Includes: bug fixes, security patches, minor enhancements, user support, 24/7 SLA per SoW 3.3.10
Y2 AED 426K | Y3 AED 447K | Y4 AED 469K | Y5 AED 490K
Total Y2-5 NET (excl WHT): AED 1,832,525 || 5-YEAR TCO: AED 4,907,333 (incl WHT)
Gate Reviews at end of each phase let Maaden exit if expectations not met - reduces our delivery risk

## Slide 6
The Team
7 unique roles deployed across the 4 phases (SoW 3.4.7 mandatory + necessary)
Programme Manager
SOW 3.4.7 mandated
Deployment: M1-M12
Single point of contact, gate reviews, Maaden steering
Solution Architect
SOW 3.4.7 Sr Functional/Technical
Deployment: M1-M12
Platform + integration architecture, code reviews, IP design
Senior Database Administrator
SOW 3.4.7 mandated
Deployment: M1-M12 (0.5 in M1)
DB schema, performance, backup + DR
Documents Controller
SOW 3.4.7 mandated
Deployment: M1-M12
Document control, transmittals, evidence pack
KSA Compliance / Security Lead
SOW 3.4.4 mandatory
Deployment: M1-M12
NCA ECC + PDPL + CCRF compliance, SIEM integration
TEAM SUMMARY
7 unique roles
Peak: 5.5 FTE (Phase 1)
Avg: 4 FTE across 12 months
Total Y1: ~33 FTE-months
Mix: 40% Onsite RAK
60% Offsite Dubai
Year 2-5 Run Team:
2-3 FTE shared pool
Lean post-handover support
AI / ML Engineer
SOW 3.3.4 - delivery of AI
Deployment: M2-M12
4 production AI agents trained on Maaden data
Module Specialist
SOW 3.3.4 - module build
Deployment: M2-M12
Builds 5 modules from scratch
Same person carries across phases - we do not duplicate headcount per phase. Onsite presence in Ras Al-Khair per SoW 3.4.6

## Slide 7
Timeline
52-week programme from PO + Y2-5 maintenance window
M1
M2
M3
M4
M5
M6
M7
M8
M9
M10
M11
M12
Phase 1 - Setup
Phase 1 - Setup
Phase 2 - Pilot Build
Phase 2 - Pilot Build
Phase 3 - Validation
Phase 3 - Validation
Phase 4 - Full Rollout
Phase 4 - Full Rollout
Gate / Milestones
M1
20%
M2
25%
M3
20%
M4
25%
M5
10%
Payment Milestones: M1 Phase 1 mob | M2 Pilot Acceptance | M3 KPI Gate | M4 Go-Live + IP Transfer | M5 Hyper-care Exit
Year 2 - Year 5: Annual Maintenance Contract (renewable at each anniversary)
KEY DATES
Contract effective date:
TBC (assumes within 90 days of bid)
Phase 1 Mobilisation:
Week 4 (end Month 1)
Phase 2 Pilot Live:
Week 12 (end Month 3)
Phase 3 KPI Gate:
Week 16 (end Month 4)
Go-Live + IP Transfer + Final Acceptance:
Week 52 (end Month 12)

## Slide 8
Commercials
Year 1 price + 5-Year Total Cost of Ownership for Maaden
YEAR 1 - TOTAL PRICE
AED 2.98M
Build Fees: AED 2,841,125
5% KSA WHT: AED 142,056
TOTAL inc WHT: AED 2,983,181
USD 812K | AUD 1.16M | SAR 3.04M
5-YEAR TCO TO MAADEN
AED 4.91M
Y1 Build: AED 2.98M
Y2-5 Maintenance: AED 1.92M
TOTAL 5-YR TCO: AED 4,907,333
USD 1.34M (excl any rollout variations)
PHASE FEE BREAKDOWN (Year 1, ex WHT)
Phase 1
Setup + Mobilisation
W 1-4
AED 232,687.50
Phase 2
Pilot Module Deployment
W 5-12
AED 625,685.00
Phase 3
Pilot Validation + Training
W 13-16
AED 269,832.50
Phase 4
Full Rollout + IP Transfer
W 17-52
AED 1,712,920.00
YEAR 1 BUILD FEES SUBTOTAL
AED 2,841,125
VS COMPETITION | Bentley iTwin: SAR 90-130M 5-Yr | Cohesive: 100-150M | Hexagon: 95-140M | XDH: SAR 5M
Pricing is in AED. Bank account AED (UAE). Payment terms 20% mobilisation + 70% progress + 10% acceptance.

## Slide 9
Risks & Open Clarifications
10 must-ask questions and how we are protected if Maaden does not answer
TOP 10 - MUST-ASK BEFORE BID SUBMISSION
A.1
Implementation duration - SoW says "XX months" - blank
A.2
Phase 4 end date - "Weeks 17+" open-ended
B.1
Module timeline conflict - 8 weeks vs 17 weeks across SoW sections
B.4
Master sequencing of 5 modules in Year 1 vs Year 2
L.1
Is this ONE bidder or TWO (SoW has 2 vendor sections)?
N.6
Is UAE-incorporated XDH acceptable as Prime?
I.1
Currency - AED, SAR, USD?
E.1
How many users?
E.2
How much data (TB)?
D.1
Which KSA cloud provider preferred?
HOW WE ARE PROTECTED
Stated XDH Assumption for each item
If Maaden does not answer, our
assumption defines bid scope
Variation Clause 4 in T&C
Scope change = re-priced under
Change Order procedure
Phase Gate Reviews
Maaden can exit at end of each
phase - limits our delivery risk
Excluded items list (Section 7)
Maaden direct procurement:
AI APIs / Hosting / GPU /
3rd-party SW / Hardware
Indicative ~SAR 40-55M over 5y
Full RFI list (60 items) submitted with our bid - see "Maaden SoW - Clarifications + XDH Assumptions.xlsx"

## Slide 10
Our Strategic Position
Why this is winnable, and what we need to do next
1. Land at low price
Maaden has not bought from a UAE small/mid vendor before. We win on: - AED 2.98M Y1 vs SAR 25-50M from Bentley/Cohesive/Hexagon - 7-person lean team - Flexible phase-gate commercial structure
2. Prove value at Pilot
Phase 2 (Weeks 5-12) is where we prove capability: - Module 3 AWP working on real ARGP data - 4 production AI agents trained on Maaden data - 5 KPI dashboards vs SoW Section 4 targets - Acceptance gate W12
3. Expand into Year 2+
Once Y1 lands, expand via: - M5 Procurement production (Y2 variation) - Module 4 Phase 2 quality features - Additional Maaden affiliates - New CV / Digital Twin scope - Multi-year recurring maintenance
NEXT STEPS
1. Finalise the 4-file bid pack (Letter, PC, Manpower, PD) - 90% complete
2. Fill Maaden Pricing Structure Template in their format - 1 day work
3. Issue formal RFI with 60-item clarification list (with XDH assumptions for protection)
4. Internal sign-off from CEO + CFO on commercial terms (margin, payment, retention)
5. Submit bid to Maaden procurement via MS EPM (per SoW 3.4.7)
6. Prepare for resource interviews (SoW 3.4.7 mandates Maaden interviews proposed team)
XD House LLC FZ | XDH-AE-Q26-05-00029 | Internal Management Briefing | June 2026