## MUST Ask - Major Queries
MAJOR QUERIES - Must Be Answered Before We Can Submit Accurate Bid
Maaden ARGP Digitalization Platform - Critical clarifications for SoW ARGP-DIGI-APP-SOW-001 Rev. 00
If these 10 items remain unanswered, our price is based on the stated assumption and any deviation will trigger Variation under Clause 4 of the Agreement.
# | SoW Ref | Major Query (must answer) | Why this matters in plain English | XDH Assumption (used if no answer)
A.1 | 3.4.6 | How many months should the project take to complete? | Maaden's own SoW says "this project should complete within XX months" - the XX is literally left blank. They forgot to fill in the number. Without this, we cannot size the team or quote a price. | 12 months Year 1 implementation following the SoW 3.3.10 phase structure
A.2 | 3.3.10 | When does Phase 4 (Full Rollout) end? | The SoW says Phase 4 is "Weeks 17+" - the plus sign means open-ended with no end date. We cannot quote a fixed price if we do not know when the work ends. | Phase 4 = Weeks 17 to 52 (8 months) ending at Go-Live and Final Acceptance
B.1 | 3.1.9, 3.2.18, 3.3.10 | Which module timeline governs the overall programme? | The SoW gives DIFFERENT timelines for different modules. Module 1 and Module 2 say 8 weeks. Module 3 says 17+ weeks. They cannot all be right - we need to know which is the master schedule. | Module 3 timeline (SoW 3.3.10) governs. Module 1 and 2 pilots run inside Phase 2 (Weeks 5-12)
B.4 | Cross-section | Please confirm master sequencing of all 5 modules across Year 1 and Year 2 | Each module has its own timeline section but they do not tie together. We need one overall plan showing what is live when, otherwise the sequence and team sizing changes. | Year 1: M1+M2+M3 pilot then production from W17, M4 Phase 1 baseline, M5 baseline only. Year 2: M2/M3 full production, M4 Phase 2, M5 production
L.1 | Sections 5 + 7 | Is Maaden tendering for ONE vendor or TWO (Systems Integrator + Software Developer)? | The SoW has TWO sections titled "Vendor Response Requirements" - Section 5 (Vendor) and Section 7 (Software Developer). It is unclear if Maaden wants one bidder doing both roles, or separate vendors. This affects who bids and how. | Single bidder delivering both roles. XDH acts as Prime + Systems Integrator + Software Developer
N.6 | (silent) | Is a UAE-incorporated entity (XDH Dubai Free Zone) acceptable as Prime bidder? | The SoW does not say if KSA incorporation is required. Some KSA tenders require KSA-licensed entity. We are UAE-based, so if KSA is required, we need a KSA partner which adds cost and time. | XDH House LLC FZ (UAE Free Zone) acceptable as Prime. KSA delivery partner engaged if Maaden requires (10-12% partner margin pass-through)
I.1 | (silent) | Which currency should we quote in (SAR, USD, AED)? | The SoW does not specify the bid currency. This affects our quote, banking, FX risk, and how Maaden's procurement evaluates our bid against KSA-based competitors. | AED with SAR equivalent shown for Maaden reference. Bank account in AED
E.1 | (silent) | How many users will use the platform? | The SoW does NOT specify how many users. We need to know user count for licensing, infrastructure sizing, and training. A platform for 50 users vs 5000 users has very different costs. | 500 named users Year 1 (60 admin, 440 end users). 150 concurrent peak. 50% growth Year 2
E.2 | (silent) | How much data will the system handle (documents, BIM models, point clouds)? | The SoW does NOT specify data volumes. 1 TB vs 100 TB requires very different storage and processing capacity, with massive cost difference. | 5 TB Year 1: 50K documents, 200 BIM models, 2 TB point clouds, 1 TB project data. Growth 30% p.a.
D.1 | 3.4.4 IT Security | Which KSA in-Kingdom cloud provider should we deploy on? | The SoW says "must be hosted in KSA" but does not say which provider. Azure Riyadh, Oracle Riyadh, STC Cloud, NEOM each have different costs and capabilities. We need to know to size hosting. | Microsoft Azure Riyadh Region (primary) + Azure Jeddah (DR). Both KSA. Procured by Maaden direct
COMMERCIAL POSITION STATEMENT
XDH House LLC FZ has reviewed Maaden's SoW (Ref ARGP-DIGI-APP-SOW-001 Rev. 00) and identified 10 critical items where the SoW is silent, ambiguous, or contains placeholders (such as the "XX months" gap in Section 3.4.6). Our bid price is based on the stated XDH Assumptions for each item. If Maaden's position on any item differs from our stated assumption, the resulting scope or schedule change will be processed under the Variation clause of the Agreement (Clause 4) with adjustment to fees, programme, or both as appropriate. We respectfully request written clarification from Maaden Procurement on the above 10 items prior to or during bid evaluation, so the final award is based on a fully aligned understanding of scope and commercials. Additional clarifications of HIGH and MEDIUM priority are listed in the second sheet of this workbook.

## RFI Items
Maaden ARGP Digitalization Platform - Clarifications & XDH Assumptions
RFI to Maaden Procurement - based on SoW ARGP-DIGI-APP-SOW-001 Rev. 00 (02/04/2025)
XDH Ref: XDH-AE-Q26-05-00029 ¦ Date: 2026.06.17
# | SoW Ref | Priority | Clarification we are asking Maaden | Why we are asking (in plain English) | XDH Assumption (used if no answer)
A. EXPLICIT BLANKS / PLACEHOLDERS IN THE SOW
A.1 | 3.4.6 | MUST | How many months should the project take to complete? | Maaden's own SoW says "this project should complete within XX months" - the XX is literally left blank. They forgot to fill in the number. Without this, we cannot size the team or quote a price. | 12 months Year 1 implementation following the SoW 3.3.10 phase structure
A.2 | 3.3.10 | MUST | When does Phase 4 (Full Rollout) end? | The SoW says Phase 4 is "Weeks 17+" - the plus sign means open-ended with no end date. We cannot quote a fixed price if we do not know when the work ends. | Phase 4 = Weeks 17 to 52 (8 months) ending at Go-Live and Final Acceptance
A.3 | 3.4.9 | HIGH | Please share the master Agreement template referenced in the SoW | The SoW mentions "the default 30-day Review Period set forth in the Agreement" but does not attach the Agreement. We need to see the contract terms before we agree to them. | Maaden has 30 days to review each deliverable; if no rejection in 30 days, it is deemed accepted
B. CONFLICTING TIMELINES BETWEEN MODULES
B.1 | 3.1.9, 3.2.18, 3.3.10 | MUST | Which module timeline governs the overall programme? | The SoW gives DIFFERENT timelines for different modules. Module 1 and Module 2 say 8 weeks. Module 3 says 17+ weeks. They cannot all be right - we need to know which is the master schedule. | Module 3 timeline (SoW 3.3.10) governs. Module 1 and 2 pilots run inside Phase 2 (Weeks 5-12)
B.2 | 3.4 Phase 1 vs 2 | HIGH | Which Module 4 sub-modules belong in Phase 1 vs Phase 2? | Module 4 (Quality) is split into "Phase 1 Baseline" and "Phase 2 Next" but the SoW does not list which specific sub-modules are in each phase. We do not know what to build first. | Phase 1 = RFI/MIR + NCR + QOR + ITP digitisation (Year 1). Phase 2 = MTC + welding traceability + AI predictive quality (Year 2)
B.3 | 3.5 | MEDIUM | When does Module 5 (Procurement) go live? | Module 5 has NO implementation timeline in the SoW - it just describes what it should do. We need to know if it goes live Year 1 or Year 2. | Module 5 = Year 2 production. Year 1 includes baseline configuration only
B.4 | Cross-section | MUST | Please confirm master sequencing of all 5 modules across Year 1 and Year 2 | Each module has its own timeline section but they do not tie together. We need one overall plan showing what is live when, otherwise the sequence and team sizing changes. | Year 1: M1+M2+M3 pilot then production from W17, M4 Phase 1 baseline, M5 baseline only. Year 2: M2/M3 full production, M4 Phase 2, M5 production
C. MAADEN-SIDE EXISTING SYSTEMS (drive integration scope)
C.1 | 3.4.4 | HIGH | Which middleware platform does "Maaden Middleware" refer to? | The SoW says we must integrate with "Maaden Middleware" but does not name the product. Without knowing which platform (MuleSoft, BizTalk, Oracle, etc.) we cannot estimate integration build time. | Microsoft BizTalk or Azure Service Bus assumed. XDH will build REST/SOAP adapters per Maaden API contract
C.2 | 3.4.4 | HIGH | Which ALM (Application Lifecycle Management) tool does Maaden use? | The SoW says we must use "Maaden ALM tool" for DevSecOps but does not name it. Each ALM (Azure DevOps, GitLab, Jira) has different setup effort. | Azure DevOps Services on KSA tenancy
C.3 | 3.4.4 | HIGH | Which low-code platform should mobile extensions be built on? | The SoW says we must extend to "Maaden low-code platform" but does not name it. Power Platform, OutSystems, and Mendix are all different products requiring different skills. | Microsoft Power Platform (Power Apps + Power Automate)
C.4 | 3.4.4 | HIGH | Which SIEM platform does Maaden use for security event logging? | The SoW requires our system to send security events to "Maaden SIEM" but does not say which one. Each SIEM (Splunk, QRadar, Sentinel) needs a different log format. | Microsoft Sentinel. XDH provides standard CEF/Syslog event format
C.5 | 3.4.4 | HIGH | Which identity provider is master: ADFS or Azure AD? | The SoW mentions BOTH ADFS AND Azure AD for authentication. We need to know which one is the master identity store so we wire up SSO correctly. | Azure AD master + ADFS secondary for legacy app federation. SSO via SAML 2.0 / OAuth 2.0
C.6 | 3.4.4 | MEDIUM | Which database technology should the new platform use? | The SoW says use "Microsoft, Oracle" databases - both are listed but no preference given. We need to pick one as primary for our build. | Microsoft SQL Server (Azure SQL Managed Instance, Riyadh region). Oracle integration via JDBC where Maaden ERP demands
C.7 | 3.4.4 | MEDIUM | Which BI/data tools are mandatory at Go-Live (Informatica, Denodo, Oracle DW, Power BI)? | The SoW lists FOUR data tools that we should integrate with. Integrating with all four takes a lot more time than just one. We need to know which are required at Go-Live. | Power BI included Year 1. Informatica, Denodo, Oracle DW integrations are Year 2 variations
C.8 | 3.4.4 | MEDIUM | Which Oracle ERP version and modules should we integrate with? | The SoW mentions "Oracle ERP Fusion Cloud" but Oracle ERP has many modules (Finance, Project Management, Supply Chain, etc.). We need to know which modules to integrate with. | Oracle ERP Fusion Cloud current major release. Modules: FI, PM (Project Management), PS, PJC
C.9 | 3.4.7 | MEDIUM | Which version of MS EPM (Microsoft Enterprise Project Management) should we use? | The SoW says project plans, status, milestones must be posted on "MS EPM System" but does not say which version. Project Server, Project Online, and Project for the Web are 3 different products. | Microsoft Project Online (Project for the Web)
D. HOSTING & DATA RESIDENCY
D.1 | 3.4.4 IT Security | HIGH | Which KSA in-Kingdom cloud provider should we deploy on? | The SoW says "must be hosted in KSA" but does not say which provider. Azure Riyadh, Oracle Riyadh, STC Cloud, NEOM each have different costs and capabilities. | Microsoft Azure Riyadh Region (primary) + Azure Jeddah (DR). Both KSA. Procured by Maaden direct
D.2 | 4.1 | HIGH | Single-tenant or multi-tenant architecture - is single-tenant acceptable? | The SoW says "multi-tenant SaaS" but ALSO says data must stay in KSA with strict isolation. These two requirements can conflict. Single-tenant is safer for compliance but costs more. | Single-tenant deployment on Maaden's KSA cloud tenancy to satisfy NCA ECC data isolation
D.3 | 3.4.4 | MEDIUM | Which level of SOC 2 and ISO certifications does hosting need (Type 1 vs Type 2)? | The SoW says "ISO, SOC 2" but does not specify SOC 2 Type 1 (lighter) or Type 2 (more rigorous, costs more), or which ISO levels (27001 vs 27017 vs 27018). | Azure Riyadh holds ISO 27001, ISO 27017, ISO 27018, SOC 2 Type 2 - all inherited by deployment
D.4 | 3.4.4 | MEDIUM | 24/7 monitoring - vendor responsibility or Maaden SOC responsibility? | The SoW says "monitored 24/7" but does not say who monitors what. Vendor monitors performance issues; Maaden SOC monitors security threats. We need to know the split. | Hybrid: vendor NOC monitors platform health (Tier 1-2). Maaden SOC monitors security events via SIEM integration
E. USER COUNTS & DATA VOLUMES (drive sizing)
E.1 | silent | HIGH | How many users will use the platform? | The SoW does NOT specify how many users. We need to know user count for licensing, infrastructure sizing, and training. A platform for 50 users vs 5000 users has very different costs. | 500 named users Year 1 (60 admin, 440 end users). 150 concurrent peak. 50% growth Year 2
E.2 | silent | HIGH | How much data will the system handle (documents, BIM models, point clouds)? | The SoW does NOT specify data volumes. 1 TB vs 100 TB requires very different storage and processing capacity. | 5 TB Year 1: 50K documents, 200 BIM models, 2 TB point clouds, 1 TB project data. Growth 30% p.a.
E.3 | 3.4.7 | HIGH | How many years of historical data should we migrate from existing systems? | The SoW asks the Implementer to "discuss preferred conversion approach... amount of history to be converted" - Maaden hasn't decided. Migrating 1 year vs 10 years has massive cost impact. | 3 years historical data migrated. XDH builds ETL; Maaden provides cleansed source data
E.4 | silent | MEDIUM | Is the scope only ARGP, or other Maaden affiliates too (MPC, Aluminium, Phosphate)? | The SoW is specifically about ARGP but Maaden has multiple affiliates. We need to know if other affiliates are included or future variations. | ARGP primary affiliate only Year 1. Additional affiliates priced as per-affiliate variation
F. AI & ADVANCED CAPABILITIES
F.1 | 5.2 | MEDIUM | Who provides the sample data for the live QSRA demonstration? | The SoW requires a live QSRA demo during bid evaluation but does not say who provides the dataset. Using Maaden real data vs our reference data takes very different prep effort. | XDH uses own anonymised reference dataset from prior mining/megaproject deployments
F.3 | silent | MEDIUM | How many AI agents are expected in Year 1 vs Year 2? | The SoW describes AI capabilities but does not specify a count. We need to know if it is 4 agents or 40 agents. | 4 production AI agents Year 1 (ingest classifier, ontology mapper, anomaly detector, KPI synthesiser). 4 more Year 2
F.4 | 3.3.4 | MEDIUM | Computer Vision and Digital Twin - production at Year 1 or Year 2? | The SoW mentions both Computer Vision (CV) and Digital Twin (DT) as features but does not say when they go live. Both are heavy AI workloads that need GPUs. | Year 1 pilot only (CV on selected ARGP area). Year 2 production rollout
G. ROLES, TEAM & MAADEN COMMITMENT
G.1 | 3.4.7 | HIGH | What minimum experience and certifications should each role have? | The SoW lists mandatory roles (PM, Sr DBA, Sr Consultants, Doc Controller) but does not say minimum years of experience or required certifications. This drives cost. | PM 15+ years PMP. Sr Functional/Technical 10+ years certified. Sr DBA 10+ years Oracle OCP / Microsoft data certified
G.2 | 3.4.7 | HIGH | How senior is "very senior" Project Manager? | The SoW says PM must be "very senior" but does not define what that means. A 10-year PM vs 25-year PM have very different cost rates. | 15+ years total experience. 5+ years PM on enterprise digitalization. 2+ similar implementations
G.3 | 3.4.6 | HIGH | How many people must be onsite in Ras Al-Khair vs offshore? | The SoW says team "stationed in Ras Al-Khair" but allows "selected team members" to travel to other affiliates. The % onsite vs offshore makes a big difference to cost (travel, per diem). | 40% onsite RAK (peak Phase 2-4). 60% offshore Dubai. Riyadh HQ travel ~2 trips/month per Sr resource
G.4 | 3.4.8 | HIGH | How much time and what roles will Maaden commit from its side? | The SoW asks Implementer to describe what Maaden's involvement should be - meaning Maaden has NOT committed any internal time. We need their team availability to plan our work. | Maaden: 1 PM (50% FTE), 5 SMEs per module (20%), 1 Executive Sponsor (5%), 1 IT lead (30%), 1 Security lead (20%)
G.5 | silent | MEDIUM | English only or English + Arabic for UI/training/docs? | The SoW does not specify working language. Doing everything bilingual roughly doubles the documentation and training cost. | English for platform UI, documentation, training. Arabic localisation as Year 2 variation
H. ACCEPTANCE, KPIs & MILESTONES
H.1 | KPIs | MEDIUM | What is the baseline against which KPI improvements are measured? | The SoW lists KPIs like "40% reduction in NCR closure time" - reduction from WHAT? Without a baseline we cannot prove we hit the target. | Baseline = Maaden current state metrics measured during Phase 1 (Weeks 1-4) before XDH solution deployed
H.2 | 3.3.7 | MEDIUM | What are the specific acceptance criteria for each deliverable (D1 to D7)? | The SoW lists 7 deliverables but does not say how Maaden will measure if each is acceptable. Without acceptance criteria we cannot prove completion. | XDH proposes per-deliverable acceptance criteria in Phase 1 BEP, signed off by Maaden by Week 4
H.3 | 3.3.10 | MEDIUM | What are the specific Phase 3 KPI gate pass criteria? | The SoW mentions a KPI Gate at Week 16 but does not say which KPIs must pass or the pass threshold. Without this, Maaden could reject Phase 3. | Pass criteria: meet 3 of 5 SoW Section 4 KPIs at minimum thresholds defined per H.1 baseline
H.4 | silent | MEDIUM | What is the variation / change request procedure? | The SoW does not specify how changes are agreed and approved. Without this, changes get stuck and we cannot get paid for extra work. | Variations within 5% of contract value approved by Maaden PM in 10 working days. > 5% requires Steering Committee
H.5 | silent | HIGH | What are the liquidated damages / late delivery penalties? | The SoW does not specify penalty rates. We need to know what we are exposed to if we are late, otherwise penalties could be unlimited. | 0.05% per day of delayed milestone fee, capped at 5% of milestone value. Carve-out for Maaden-caused delays
H.6 | 3.4.9 | MEDIUM | How long does Maaden have to review each deliverable? | The SoW references "default 30 days set in the Agreement" but the Agreement is not attached. We need this to know our cashflow timing. | 30 days per deliverable with deemed acceptance if no rejection in 30 days
I. COMMERCIAL TERMS NOT IN SOW
I.1 | silent | MUST | Which currency should we quote in (SAR, USD, AED)? | The SoW does not specify the bid currency. Affects our quote, banking, FX risk. | AED with SAR equivalent shown for Maaden reference. Bank account in AED
I.2 | silent | HIGH | What are Maaden's standard payment terms (Net 30, 45, 60)? | The SoW does not specify when Maaden pays. Net 30 vs Net 90 changes cashflow significantly. | Net 30 days from invoice acceptance
I.3 | silent | HIGH | Is there retention (% withheld until completion)? | The SoW does not mention retention. KSA contracts often have 10% retention - we need to know if this applies and how long it is held. | 10% retention on each milestone, released at end of 1-month hyper-care
I.4 | silent | MEDIUM | Is a performance bond / bank guarantee required? | The SoW does not mention bonds. KSA megaprojects sometimes require 5-10% performance bonds which cost money to provide. | None proposed. If required: 5% of Year 1 contract value, valid 12 months, bond cost passed through
I.5 | silent | HIGH | 5% KSA Withholding Tax - applies to services only or also to license/IP fees? | The SoW does not address WHT. We need to know if the 5% WHT applies to all fees or only services - this affects our NET receipts. | 5% WHT applies to service fees only (not pure license/IP fees) per ZATCA
I.6 | 3.4.9 | MEDIUM | What are the per diem and travel reimbursement rates? | The SoW says "per diem and round trip air travel reimbursement apply for assignments of less than 90 days" but does not give rates. | Per diem AED 800/day. Air travel reimbursed at economy + 1 round trip per 4-week tour
I.7 | 3.4.9 | HIGH | Does Maaden prefer fixed-fee or Time & Material? | The SoW asks the Implementer to describe but does not state Maaden's preference. Fixed-fee transfers delivery risk to vendor; T&M to Maaden. | Fixed-fee per phase per SoW 3.3.10 structure. T&M rates apply to variations only
I.8 | silent | MEDIUM | Is Year 2-5 maintenance part of Year 1 quote or tendered later? | The SoW does not say if maintenance must be priced now or later. We have included it as 15% of build cost for Year 2 onwards. | Year 2-5 maintenance quoted as 15% of Year 1 build cost base, escalated 5% p.a.
J. TRAINING & DOCUMENTATION
J.1 | 3.4.7 | MEDIUM | How many users to train, where, and what allowance? | The SoW asks Implementer to describe "training allowance bundled in cost" and "limits on number of employees" - meaning Maaden hasn't decided. 30 trainees vs 300 trainees is very different cost. | 8 user modules + 1 admin guide. 30 train-the-trainer attendees in Phase 3. Onsite RAK + Riyadh + virtual. > 30 trainees per head charge
J.2 | 3.4.5 | LOW | In which language(s) should the 6 manuals be delivered? | The SoW lists 6 mandatory manuals but does not say if English only or bilingual. Translation doubles the documentation cost. | English PDF + searchable online help, version-controlled in Azure DevOps wiki
K. STANDARDS & COMPLIANCE
K.1 | Section 6 | MEDIUM | Which of the 7 standards must vendor hold certifications for vs just comply with? | The SoW lists 7 standards. There is a big difference between vendor holding ISO 27001 certificate (expensive, takes time) vs vendor delivering an ISO 27001-compliant solution. | XDH delivers solution compliant with all 7. XDH holds ISO 27001. Cloud provider holds SOC 2, ISO 27017/27018. ISO 9001 + NCA ECC + PDPL evidence at Final Acceptance
K.2 | 3.4.4 | MEDIUM | Who chooses and pays for the penetration testing firm? | The SoW says "qualified individuals (internal and/or external 3rd parties)" must do pentest. Maaden may want their own pentest firm; this costs money. | NCA-licensed KSA pentest firm (CrowdStrike, EY KSA, or equivalent) selected by Maaden, paid by Maaden as Exclusion item
K.3 | 3.4.4 | LOW | How often must we report PDPL compliance? | The SoW says report regularly "to be defined with focal point later" - frequency not yet set. Monthly vs quarterly reporting effort differs. | Quarterly PDPL compliance reports + immediate breach notification within 24 hours
L. STRUCTURAL CONFLICT IN SOW
L.1 | Sections 5 + 7 | MUST | Is Maaden tendering for ONE vendor or TWO (Systems Integrator + Software Developer)? | The SoW has TWO sections titled "Vendor Response Requirements" - Section 5 (Vendor) and Section 7 (Software Developer). It is unclear if Maaden wants one bidder doing both roles, or separate vendors. This affects who bids and how. | Single bidder delivering both roles. XDH acts as Prime + Systems Integrator + Software Developer
M. EXIT, IP & CONTINUITY
M.1 | 1.4 | HIGH | What exit strategy, IP ownership terms, and source code escrow are required? | The SoW mentions "exit strategies" as a risk mitigation but does not define terms. Owning IP vs licensing IP is a massive commercial difference for both parties. | Exit: 90-day data export window. IP: Maaden owns data + Maaden-specific customisations. XDH retains platform IP. Source code escrow via Iron Mountain / NCC Group
M.2 | silent | MEDIUM | Data export format and timeline on termination? | The SoW does not specify data portability terms. Maaden may later demand data in proprietary formats which costs to extract. | Maaden owns all data perpetually. Export in standard formats (IFC, JSON, CSV, native) within 30 days of request
N. EVALUATION & SUBMISSION
N.1 | silent | HIGH | What is the bid submission deadline and format? | The SoW does not specify when bids are due or in what format. We need to know to plan our submission. | Submission via MS EPM as referenced in SoW 3.4.7, or as instructed by Maaden procurement contact
N.2 | silent | MEDIUM | What is the evaluation criteria split (technical vs commercial)? | The SoW does not say how Maaden will score bids. 80% commercial means race to bottom; 80% technical rewards capability. | 60% technical / 40% commercial weighted. Award decision within 90 days of bid submission
N.3 | silent | LOW | How many reference projects must we submit? | The SoW does not say if reference projects are required. Standard for megaprojects. | XDH provides 3 reference projects of similar enterprise digitalization scope
N.4 | silent | MEDIUM | How long must our proposal remain valid? | The SoW does not specify proposal validity. KSA tenders sometimes ask for 180 days which exposes us to FX, rate changes. | 120 days from bid submission date
N.5 | 3.4.7 | MEDIUM | Are resource interviews in-person Riyadh or via video? | The SoW says Maaden "will interview all proposed resources" but does not say how. In-person Riyadh travel adds cost and time. | Video interview via Microsoft Teams. In-person Riyadh only for shortlisted PM and Sr Architect
N.6 | silent | MUST | Is a UAE-incorporated entity (XDH Dubai Free Zone) acceptable as Prime bidder? | The SoW does not say if KSA incorporation is required. Some KSA tenders require KSA-licensed entity. We are UAE-based. | XDH House LLC FZ (UAE Free Zone) acceptable as Prime. KSA delivery partner engaged if Maaden requires (10-12% partner margin)
PRIORITY LEGEND:
MUST | Critical - cannot price accurately without Maaden answer. Flag in cover note as pricing-dependent.
HIGH | High impact - assumption stated; if Maaden disagrees, variation applies under Clause 4.
MEDIUM/LOW | Quality of bid item - assumption acceptable unless Maaden specifies otherwise.