Fee Proposal Letter

| # Date | # Monday, June 1, 2026 |
| --- | --- |
| # Addressed to | # Mohammed Al-Shammari |
| # Customer e-mail | # procurement@maaden.com.sa |
| # Customer | # Saudi Arabian Mining Company (Maaden) |
| # Customer No. | # AE00093 MAADEN |
| # Project | # Ar Rjum Gold Project (ARGP) - Integrated AI-Powered Digitalization Platform |
| # Quotation No. | # XDH-AE-Q26-05-00029 |
| # Service | # ARGP Digitalization Platform |

| Dear Mr. Al-Shammari, | M/S Maaden |
| --- | --- |

We’re pleased to share our fee proposal for the Ar Rjum Gold Project (ARGP) digitalization platform per ARGP-DIGI-APP-SOW-001 Rev. 00. XD House LLC FZ proposes the ARGP Digitalization Platform - a purpose-built AI-powered enterprise SaaS solution covering all 5 SOW modules with the Maaden-mandated enterprise architecture (Microsoft Azure AD + MS EPM + Maaden Middleware + ALM + SIEM integration).

If you wish to proceed, please send us a purchase order or/ and sign and return the enclosed contract.

We appreciate your trust in XD House and look forward to collaborating with you.

Kind regards,

Anas Ayoub

Founder & CEO (XD House LLC FZ)

anas.ayoub@xdhouse.co

+971 555 895 395

+44 7534 7 29992

SOW

The scope covers full deployment of the ARGP Digitalization Platform aligned to SOW Section 3.3.10 phased timeline:

01: AI-Native Implementation of the ARGP Digitalization Platform per SOW 3.3.10

| Allocated Team (Year 1, 13 FTE per SOW 3.4.7): - 1 Programme Manager - 1 Solution Architects / Integration Engineers - 1 Database Administrator - 1 AI / Machine Learning Engineer - 1 KSA Compliance / Security Lead - 1 Module Specialist - 1 Documents Controller Programme (aligned to SOW 3.3.10): - Phase 1 (Weeks 1-4): Requirement Finalization, Environment Setup, Core Configuration - Phase 2 (Weeks 5-12): Pilot Module Deployment (AWP, Punch List, Pre-Commissioning) on selected ARGP area; Module 1 + Module 2 pilots (per SOW 3.1.9 + 3.2.18) run within this window - Phase 3 (Weeks 13-16): Pilot Validation, KPI Measurement, User Training, Feedback Incorporation - Phase 4 (Weeks 17+): Full-Scale Rollout across the entire ARGP project - Module 4 Phase 1 (RFI/MIR + NCR/QOR + ITP/ITR + PQI + Preservation + Vendor Inspection + Walkdowns/Punch + Dashboards) within Year 1 - Module 4 Phase 2 (Handover Dossiers + NDT + Piping Test Packages + Audit Register) Year 2 - 1-month hyper-care included at no charge post Go-Live (per SOW 3.4.5) Deliverables (per SOW 3.3.7): - D1: ARGP Digitalization Platform with all 5 modules (M1-M5) - D2: Complete integration with Maaden enterprise systems (Aconex, P6, SAP, Aveva PI, EPM, ALM, SIEM) - D3: Data Migration and Setup Plan + executed migration - D4: User Training + certified Train-the-Trainer programme - D5: System Administration + Configuration Runbooks - D6: Security & Compliance Dossier (NCA ECC + PDPL + CCRF evidence pack) - D7: COMPLETE SOURCE CODE + AI MODELS trained on Maaden data + all customizations + build artefacts + CI/CD pipelines + documentation transferred to Maaden - 1-month hyper-care post Go-Live (no charge per SOW 3.4.5) Compliance & Standards (per SOW Section 6): - ISO 19650 + ISO/IEC 27001 + ISO 9001 + CII AWP - NCA ECC-1:2018 + PDPL + CST CCRF - AES-256 encryption + TLS v1.2 minimum + SAML / WS-Federation / OAuth 2.0 | Maaden Mandated Integrations (SOW 3.4.4): - Primavera P6 (Level 4 resource + cost loaded) - Oracle ERP / SAP (cost + commitments + master data) - Revit / Navisworks / Plant 3D / P&ID - Aconex / OpenText / SharePoint document management - Power BI / Tableau + Oracle Data Warehouse + Informatica + Denodo - Aveva PI / Cognite (IIoT field data) - Microsoft Azure AD + ADFS SSO (per SOW 3.4.4) - MS EPM System (per SOW 3.4.5 project plan submission) - Maaden Middleware (per SOW 3.4.4) - Maaden ALM tool (DevSecOps per SOW 3.4.4) - Maaden SIEM (24/7 monitoring per SOW 3.4.4) KPIs (To be measured during Pilot Phase): - KPI 1: ≥30% reduction in time from Construction Complete to Mechanical Completion sign-off. - KPI 2: ≥95% of all punch items are logged and assigned an owner within 24 hours of identification. - KPI 3: ≥50% reduction in time spent by engineers compiling handover dossiers. Digitalization Scope of Work (SoW) ARGP-DIGI-APP-SOW-001 28 Classification: Public - KPI 4: 100% of pre-commissioning test records (e.g., loop sheets) are digital and directly linked to asset tags. - KPI 5: ≥15% improvement in Plan Percent Complete (PPC) for pilot work areas. - KPI 6: The platform provides a forecasted delay alert for a critical path activity at least 4 weeks in advance Exclusions - Maaden Direct Procurement (NOT in XDH price): - AI / LLM API subscriptions (Anthropic Claude, OpenAI / Azure OpenAI, Google Gemini, embedding APIs) - Maaden procures via enterprise agreement - KSA in-Kingdom hosting infrastructure (STC Cloud / MS KSA Cloud Region / AWS Bahrain / NEOM / Mobily) - Maaden procures direct - Compute / GPU infrastructure for Computer Vision + Digital Twin (NVIDIA A100 / H100 instances) - Maaden procures direct - Object storage at scale for point clouds + images + video (PB-scale over 5 years) - Maaden procures direct - Vector database (Pinecone / Weaviate / equivalent) for RAG - Maaden procures direct - Specialized third-party SaaS (Vision APIs, OCR / Document AI, GIS, Geospatial) - Maaden procures direct - Multi-affiliate / multi-site tenant deployments beyond ARGP primary - priced as Variation per affiliate - Annual compliance audit fees (ISO/IEC 27001 surveillance, SOC 2 Type 2, penetration testing, PDPL attestation) - Maaden procures direct or coordinated pass-through - Third-party software licenses (Primavera P6, Revit, Navisworks, Plant 3D, SAP, Aconex, Power BI, Aveva PI) - Maaden procures direct |
| --- | --- |

SOW

Contractual Requirements:

| S.N | Maaden SOW Module Requirement | XDH | Remarks |
| --- | --- | --- | --- |
| 01 | Module 1 - Engineering & Design Mgmt (CDE + AI checks + Digital Twin + 20 discipline checks A-T) | Y | Per SOW 3.1.1 to 3.1.10. Production Y1. |
| 02 | Module 2 - Schedule & PC (P6 + QSRA + EVMS + AWP) | Y | Per SOW 3.2.1 to 3.2.21. Pilot Y1, prod Y2. |
| 03 | Module 3 - Construction & Pre-Comm (8 integrated sub-modules) 3.1 CDE & Engineering Data Hub 3.2 Construction Management & AWP (EWP / CWP / IWP) 3.3 Pre-Commissioning & Mechanical Completion 3.4 Commissioning & Startup 3.5 Project Controls & Analytics 3.6 AI & Digital Field Verification (scan-to-BIM) 3.7 Materials Management & Traceability (QR/RFID + MTC) 3.8 Safety & Permit-to-Work (PTW + LOTO) | Y | Per SOW 3.3.1 to 3.3.10. Pilot Y1, prod Y2. |
| 04 | Module 4 - Quality Mgmt (Phase 1 baseline + Phase 2 next) Phase 1: RFI/MIR + NCR + QOR + Preservation + ITP/ITR + PQI + Vendor + Walkdowns/Punch Phase 2: Handover Dossiers + NDT + Piping Test Packages + Audit Register | Y | Per SOW 3.4.1 to 3.4.12. Phase 1 Y1, Phase 2 Y2. |
| 05 | Module 5 - Procurement & Supply Chain | Y | Per SOW 3.5.1 to 3.5.3. Y2 production. |
| 06 | AI & Analytics (QSRA + Predictive + Digital Twin + CV + MCIS) | Y | Live QSRA demo on sample data per SOW Section 5 |
| 07 | KSA in-Kingdom data residency + 24/7 monitoring | Y | NCA ECC-1 + PDPL + CCRF + SOC 2 + Maaden SIEM |
| 08 | Maaden architecture mandates (Azure AD + EPM + Middleware/ALM/SIEM) | Y | Per SOW 3.4.4 mandatory architecture |
| 09 | Required roles (Sr DBA + Documents Controller + Programme Director) | Y | Per SOW 3.4.7 mandatory team composition |
| 10 | 1-month hyper-care post Go-Live + 30-day acceptance period | Y | Per SOW 3.4.5 + 3.4.9 included |

Commercials

Pricing

Pilot Phase

| S.N | Description | Total in (AED) |
| --- | --- | --- |
| 01 | Phase 1 (Weeks 1-4) - Requirement Finalization + Setup + Core Configuration | 232,687.50 |
| 02 | Phase 2 (Weeks 5-12) - Pilot Module Deployment + AI + Integration | 625,685.00 |
| 03 | Phase 3 (Weeks 13-16) - Pilot Validation + KPI + Training | 269,832.50 |
| 04 | Phase 4 (week 17-52) - Phase 4 W17+: Rollout to entire ARGP + full M4/M5 build + hyper-care | 1,712,920.00 |
|  | Total | 2,841,125.00 |
|  | The 5% KSA WHT | 142,056.25 |
|  | Total Price (including WHT) | 2,983,181.25 |

Optional

Recurring Year 2 to Year 5

| S.N | Description | Total in (AED) Excluding WHT |
| --- | --- | --- |
| 02 | Year 02 (15% of build cost) | 426,168.75 |
| 03 | Year 03 (Year 2 x1.05 scalation) | 447,477.19 |
| 04 | Year 04 (Year 2 x1.10 scalation) | 468,785.63 |
| 05 | Year 05 (Year 2 x1.15 scalation) | 490,094.06 |
|  | Total | 4,673,650.63 |
|  | The 5% KSA WHT | 233,682.53 |
|  | Total Price (including WHT) | 4,907,333.16 |

Payment terms:

| S.N | Payment Percentage | Total in (AED) |
| --- | --- | --- |
| 01 | 20% | Mobilization |
| 02 | 80% Progress Invoice | Invoices will be shared on the 20th of each month. |
| 03 | 10% | Acceptance and Handover |

Bank Details

| Account type: | AED |
| --- | --- |
| IBAN: | AE760860000009664507760 |
| BIC/ Swift Code: | WIOBAEADXXX |
| Bank Name | Wio Business |
| Account No: | 9664507760 |
| Account Name: | XD HOUSE LLC FZ |
| Company Address | Meydan Grandstand, 6th floor, Meydan Road, Nad Al Sheba, Dubai, U.A.E, PO Box 215626 |
| Contact E-mail | anas.ayoub@xdhouse.co |

T&C

These terms and conditions (the "Agreement") govern the provision of custom software development services by the Provider (XD House LLC FZ) to the Customer (Saudi Arabian Mining Company / Maaden) for the build of the ARGP Digitalization Platform under SOW ARGP-DIGI-APP-SOW-001 Rev. 00.

Customer: Saudi Arabian Mining Company (Maaden), a publicly traded mining company headquartered in Riyadh, Kingdom of Saudi Arabia.
Provider: XD House LLC FZ, a Digital Construction firm registered in Dubai Free Zone, United Arab Emirates.
Project Duration: 12-month Year 1 custom build aligned to SOW 3.3.10 phases + Years 2-5 optional Maintenance contract.

1. Scope of Services
1.1 Provider (XD House) agrees to design, develop, integrate, deploy, and hand over the ARGP Digitalization Platform per SOW ARGP-DIGI-APP-SOW-001 Rev. 00.
1.2 Services will be delivered in accordance with the agreed-upon project duration stated at the top of this Agreement. Any changes will be communicated in writing.

1.3 Customer acknowledges that Provider (XD House) is based in Dubai and that services may be subject to local laws and regulations.

2. Fees and Payment
2.1 Fees are as set out in the Agreement, with additional work charged separately.
2.2 Payment shall be made via bank transfer within four (4) calendar days of invoice.
2.3 In the event of late payment, the Client agrees to pay a late payment charge of 1.5% of the overdue amount. This charge is intended solely to cover administrative and recovery costs arising from the delay. Any amount exceeding such costs shall not constitute income to the Company and shall be donated to charity.
2.4 Customer payments must include coverage for bank charges.
2.5 If the Customer issues a PO or WO with different payment terms, those new terms will apply only to payment; all other terms of this Agreement remain valid.

3. Customer Responsibilities
3.1 Provide KSA in-Kingdom cloud tenancy (Azure Riyadh / Oracle Riyadh / STC Cloud) provisioned and accessible by W2.
3.2 Provide all enterprise system access (Azure AD, ADFS, EPM, ALM, SIEM, Aconex, Primavera P6, SAP, Aveva PI) with credentials and sandbox environments by W2.
3.3 Nominate one Maaden Project Manager (SOW 3.4.7) as single point of contact, plus designated SMEs per ARGP discipline.
3.4 Provide Maaden production-like test data for AI model training and pilot validation.
3.5 Maaden carries direct procurement of all items in the Exclusions list (AI APIs, KSA hosting, GPU, vector DB, third-party software, hardware, compliance audits).
3.6 Respond to RFIs within five (5) working days. Late responses may trigger programme adjustments under Clause 4 Variations.
3.7 Provide all reference data, drawings, and standards required for ARGP context within ten (10) working days of contract effective date.
3.8 Notify Provider in writing of any delays or scope changes affecting the programme.

4. Variations
4.1 Changes outside the SOW scope require written Change Order approval signed by both parties.
4.2 Change Orders shall be reviewed and responded to within ten (10) working days. If no response, Provider may adjust programme or fees.
4.3 Change Orders are calculated pro-rata using the Time Charge Rates in this Agreement (Table 9).
4.4 Variations include but are not limited to: (a) acceleration of programme; (b) multi-shift / weekend / night working; (c) Maaden-driven re-sequencing of phases or modules; (d) additional modules beyond M1-M5; (e) additional AI agents beyond the 8 standard; (f) multi-affiliate tenants beyond ARGP primary; (g) re-work from late or revised Maaden inputs; (h) major new features beyond the 5% per year minor-enhancement allowance under Maintenance.

5. Exclusions
5.1 All exclusions apply unless explicitly included in the Scope of Works with a clear price breakdown and possibly additional terms.
5.2 Exclusions explicitly include (Maaden direct procurement): (a) AI / LLM API subscriptions (Anthropic Claude, OpenAI, Azure OpenAI, Google Gemini, embeddings); (b) KSA in-Kingdom hosting (Azure Riyadh, Oracle Riyadh, STC Cloud, NEOM, Mobily); (c) Compute / GPU infrastructure (NVIDIA A100/H100); (d) Object storage at scale; (e) Vector database (Pinecone, Weaviate); (f) Specialized SaaS (Vision APIs, OCR, GIS); (g) Multi-affiliate tenants beyond ARGP primary; (h) Annual compliance audits (ISO 27001 surveillance, SOC 2 Type 2, pen test, PDPL attestation); (i) Third-party software licences (Primavera P6, Revit, SAP, Aconex, Power BI, Aveva PI); (j) Hardware (laptops, IIoT sensors, RFID).

6. QA/QC Protocols
6.1 All software deliverables follow agreed development standards
6.2 Phase Gate Reviews at end of each phase: Phase 1 acceptance memo, Phase 2 pilot acceptance, Phase 3 KPI gate pass, Phase 4 Final Acceptance.
6.3 KPI measurement per SOW Section 4 metrics during Phase 3 validation; remediation of any P1 or P2 defects before Phase 4 commencement.
6.4 All deliverables version-controlled in the source code repository handed over to Maaden at Final Acceptance.

7. Programme and Delivery
7.1 Delivery timelines will align with the agreed project duration stated at the top of this Agreement, starting from receipt of reference files, LPO, and mobilisation payment.
7.2 Regular updates and open communication will be maintained.
7.3 In case of unforeseen circumstances, both parties will collaborate to minimise impact.

8. Intellectual Property Rights 
8.1 At Final Acceptance , Customer (Maaden) becomes the sole owner of all intellectual property created under this Agreement, including without limitation: (a) complete platform source code; (b) AI models trained on Maaden Data; (c) custom AI agents; (d) all configurations, customisations, scripts, integrations, and integration adapters; (e) build artefacts and CI/CD pipelines; (f) data schemas, migration tools, and seed data; (g) all technical, user, and operational documentation.
8.2 Provider (XD House) transfers all such IP to Customer at Final Acceptance via written IP Assignment Certificate. Provider retains no rights to reuse, license, sublicense, or offer the Maaden-built platform code or trained AI models to any other party.
8.3 Customer Data (Maaden Data) is always and exclusively owned by Customer. Provider has no right, title, or interest in Maaden Data at any time.

8.4 Provider retains generic background IP that existed prior to this Agreement (such as software engineering methodologies, internal frameworks, and team know-how). This excludes anything built specifically under this Agreement.
8.6 Provider warrants that all IP delivered is original or properly licensed, free from third-party claims, and Provider indemnifies Customer against any third-party IP infringement claims arising from the delivered platform.

9. Termination
9.1 Either party may terminate with sixty (60) days written notice during Phase 1-4 build. Customer pays for work completed plus reasonable wind-down costs up to a maximum of 10% of the next phase fee.
9.2 Either party may terminate immediately on material breach uncured for thirty (30) days after written notice.

10. Confidentiality & Data Protection
10.1 Both parties agree to confidentiality except as required by law. 10.2 Compliance with data protection laws is mandatory.

11. Liability and Indemnification
11.1 Provider (XD House) will exercise reasonable care and skill.
11.2 Not liable for loss/damage outside its control.
11.3 Customer is responsible for timely review of deliverables.
11.4 Customer indemnifies Provider (XD House) against claims arising from failure to review.

12. Dispute Resolution & Governing Law
12.1 Disputes to be resolved first via good faith negotiations. 12.2 If unresolved after 30 days, proceed to mediation before legal action.
12.3 Mediation costs shared equally.
12.4 This Agreement shall be governed by and construed in accordance with the laws of Dubai.