## Queries and Assuption
XDH Clarifications for SoW ARGP-DIGI-APP-SOW-001 Rev. 00
# | SoW Ref | Queries | Description | XDH Assumption
1 | 3.4.6 | How many months should the project take to complete? | Maaden's SoW says "this project should complete within XX months" - Please confirm the duration | 10 months (40 weeks) Year 1 implementation per XDH Master Roadmap XDH-AE-Q26-05-00030, following the SoW 3.3.10 phase structure
2 | 3.3.10 | When does Phase 4 (Full Rollout) end? | The SoW says Phase 4 is "Weeks 17+" - Please confirm the expection duration of Phase 4. | Phase 4 = Weeks 17 to 40, split 4a-4d (M1 CDE W17-24, M4 Quality W21-29, M5 Procurement W25-32, Handover W33-40), ending at Final Acceptance W40
3 | 3.1.9, 3.2.18, 3.3.10 | Which module timeline governs the overall programme? | The SoW gives DIFFERENT timelines for different modules. Module 1 and Module 2 say 8 weeks. Module 3 says 17+ weeks. Please confirm the Timeline to follow | Module 3 timeline (SoW 3.3.10) governs. Module 1 and 2 pilots run inside Phase 2 (Weeks 5-12)
4 | N/A | Please confirm master sequencing of all 5 modules across Year 1 and Year 2 | Each module has its own timeline section but they do not tie together. Please provide one overall plan showing what is live when. | Single 40-week programme per Master Roadmap: Phase 2 pilots M2 AWP + M3 Pre-Comm (W5-12); Phase 4 delivers M1 CDE, M4 Quality, M5 Procurement to full production; all 5 modules live by W40. Years 2-5 = maintenance + enhancements
5 | N/A | How many users will use the platform? | The SoW does NOT specify how many expected users. Please verify | 500 named users Year 1 (60 admin, 440 end users). 150 concurrent peak. 50% growth Year 2
6 | N/A | How much data will the system handle (documents, BIM models, point clouds)? | The SoW does NOT specify data volumes. 1 TB vs 100 TB requires very different storage and processing capacity, with massive cost difference. | 5 TB Year 1: 50K documents, 200 BIM models, 2 TB point clouds, 1 TB project data. Growth 30% p.a.
7 | 3.4.4 IT Security | Verify cloud provider in KSA. | The SoW says "must be hosted in KSA".Please verify the expected host (Azure Riyadh, Oracle Riyadh, STC Cloud, etc.) | Microsoft Azure Riyadh Region (primary) + Azure Jeddah (DR). Both KSA. Procured by Maaden direct
8 | 3.3.7 | What are the specific acceptance criteria for each deliverable (D1 to D7)? | The SoW lists 7 deliverables but does not specify the Criteria
9 | 3.1.2 / Roadmap M1 | Which class library baseline governs Data Templates - CFIHOS/ISO 15926-4 or a Maaden internal library? | Client vision diagrams define Standard->Product Type->Property Set->Data Template. The baseline dictionary determines mapping effort. | CFIHOS-aligned library seeded from Maaden MCIS + project specs; Maaden to confirm within Phase 1 W2
10 | 3.1.3 | Who owns the tag numbering convention (format, registers, uniqueness rules)? | Vision image 1 shows governed IDs+REVs (e.g. EQP-000789 Rev A). Tag format must be locked before Master Data Registry build. | Maaden Engineering issues the convention; XDH enforces via registry validation rules
11 | 3.4.4 / Roadmap Integrations | Which downstream system should receive the FIRST live connector? | 10 integrations planned. First connector proves the publish pipeline end-to-end. | Oracle Aconex (documents) or Primavera P6 (schedule) in Phase 1-2 per roadmap; Maaden to prioritize
12 | 3.3.10 / Roadmap Phase 2 | Which ARGP area is the pilot area for M2/M3 (and CDE registry seed data)? | Pilot scope needs a bounded area with active construction data. | Maaden PMO nominates one area (e.g. CIL circuit) by end of Phase 1 W3
13 | Roadmap T-171/T-173 | Confirm acceptance to build the Master Data Registry core in Phase 1-2 (ahead of roadmap Phase 4a). | M2 AWP and M3 Pre-Comm pilots consume tags/hierarchy/templates; building the registry core early de-risks the pilot and matches the client vision diagrams. | Registry core (MEL, tag register, hierarchy, data templates) delivered by W8; full M1 (model viewer, intelligent P&ID) stays in Phase 4a